## WBS Hierarchy Details
WBS ID :
Project WBS Hierarchy Details
Sub Project | All
Generated On | Mon Jun 22 12:27:49 IST 2026 ,By Rohit Ingale
Project Name | Zen Kode Building 1
WBS Name | Total Qty | Unit | Days | Amount | WBS / Activity Code | Rate | WBS Description
Earthwork |  |  | 7 | 1,25,63,648.07 | W-Earthwork
Excavation |  |  | 3 | 90,24,279.65 | W-Excav
Backfilling |  |  | 2 | 18,06,221.99 | W-Backfill
Att |  |  | 1 | 2,66,944.51 | W-Att
Rubble-Soiling |  |  | 1 | 14,66,201.92 | W-Rub-Soil
Rcc Work |  |  | 212 | 59,76,38,133.35 | W-Rcc Work
Pcc |  |  | 1 | 30,91,069.00 | W-Pcc
Rmc-Conventional |  |  | 166 | 34,14,98,722.84 | W-Rmc-Con
Reinforcement |  |  | 24 | 20,57,64,706.65 | W-Reinf
PT Tendons |  |  | 21 | 4,72,83,634.86 | W-Pt
Masonary & Plaster |  |  | 5 | 4,36,81,098.38 | W-Masonary & Plaster
Blockwork |  |  | 1 | 1,59,36,103.97 | W-Blockwork
Internal Plaster |  |  | 2 | 49,48,683.41 | W-Internal Plaster
External Plaster |  |  | 1 | 64,43,804.92 | W-External Plaster
Gypsum Plaster |  |  | 1 | 1,63,52,506.08 | W-Gypsum Plaster
Waterproofing |  |  | 12 | 1,64,02,293.33 | W-Waterproofing
Waterp |  |  | 12 | 1,64,02,293.33 | W-Waterp
Doors & Wooden Work |  |  | 1 | 86,57,945.95 | W-Doors & Wooden Work
Doors |  |  | 1 | 86,57,945.95 | W-Doors
Windows & Sliding Door |  |  | 1 | 81,48,655.01 | W-Windows & Sliding Door
Sliding Windows |  |  | 1 | 81,48,655.01 | W-Sliding Windows
Flooring & Tiling |  |  | 26 | 4,16,36,791.41 | W-Flooring & Tiling
Flooring |  |  | 11 | 2,91,97,562.88 | W-Flooring
Skirting |  |  | 3 | 12,97,931.43 | W-Skirting
Dado |  |  | 2 | 38,14,499.99 | W-Dado
Granite & Stone Work |  |  | 10 | 73,26,797.11 | W-Granite & Stone Work
Ms & Ss Work |  |  | 1 | 45,83,618.44 | W-Ms & Ss Work
Fabrication Work |  |  | 1 | 45,83,618.44 | W-Fabrication Work
Painting & Polishing Work |  |  | 1 | 1,01,85,818.76 | W-Painting & Polishing Work
Painting Work |  |  | 1 | 1,01,85,818.76 | W-Paint
Plumbing |  |  | 1 | 56,55,000.00 | W-Plumbing
Internal Plumbing |  |  | 1 | 56,55,000.00 | W-Plumb
Electrical Work |  |  | 1 | 58,43,360.00 | W-Electrical Work
Internal Electrical |  |  | 1 | 58,43,360.00 | W-Elect
Lift |  |  | 2 | 12,85,78,700.00 | W-Lift
Lift Work |  |  | 2 | 12,85,78,700.00 | W-Lift Work
Bldg. Firefighting |  |  | 1 | 3,05,57,456.29 | W-Bldg. Firefighting
Building Firefighting |  |  | 1 | 3,05,57,456.29 | W-Bldg Ff
Elevation,Glazing & Facade Work |  |  | 1 | 10,87,33,615.31 | W-Elevation,Glazing & Facade
Glazing & Facade Work |  |  | 1 | 10,87,33,615.31 | W-Glazing & Facade Work
Bldg. Amenities |  |  | 1 | 3,13,21,392.70 | W-Bldg. Amenities
Building Amenities |  |  | 1 | 3,13,21,392.70 | W-Amenities
Misc |  |  | 1 | 50,92,909.38 | W-Misc
Miscellaneous Work |  |  | 1 | 50,92,909.38 | W-Misc Work
PL-Excavation |  |  | 3 | 90,24,279.65 | PL-W-Excav
| 13,242.766 | CUM | 1 | 18,75,175.67 | PL1298-Building 1-PL-ZC01 | 141.60 | PL-Block Excavation Soft Block Excavation Soft
| 9,932.070 | CUM | 1 | 31,64,357.50 | PL1298-Building 1-PL-ZC02 | 318.60 | PL-Block Excavation Hard Murrum Block Excavation Hard Murrum
| 9,932.070 | CUM | 1 | 39,84,746.48 | PL1298-Building 1-PL-ZC03 | 401.20 | PL-Block Excavation Hard Rock Block Excavation Hard Rock
PL-Backfilling |  |  | 2 | 18,06,221.99 | PL-W-Backfill
| 4,409.000 | CUM | 1 | 7,54,379.90 | PL1298-Building 1-PL-ZC04 | 171.10 | PL-Backfilling From Excavated Material Backfilling From Excavated Material
| 2,025.890 | CUM | 1 | 10,51,842.09 | PL1298-Building 1-PL-ZC05 | 519.20 | PL-Murrum Filling Brought from out side (Inside The Plinth) Murrum Filling Brought from out side (Inside The Plinth)
PL-Att |  |  | 1 | 2,66,944.51 | PL-W-Att
| 3,376.480 | SQM | 1 | 2,66,944.51 | PL1298-Building 1-PL-ZC06 | 79.06 | PL-Antitermite Treatment Antitermite Treatment
PL-Rubble-Soiling |  |  | 1 | 14,66,201.92 | PL-W-Rub-Soil
| 776.590 | CUM | 1 | 14,66,201.92 | PL1298-Building 1-PL-ZC07 | 1,888.00 | PL-Rubble Soiling Rubble Soiling
PL-Waterproofing |  |  | 3 | 68,22,428.66 | PL-W-Waterproofing
| 818.280 | CUM | 1 | 9,65,570.40 | PL1298-Building 1-PL-ZC08 | 1,180.00 | PL-Box Type Waterproofing Lift Box Type Waterproofing Lift
| 3,647.520 | CUM | 1 | 41,31,910.66 | PL1298-Building 1-PL-ZC09 | 1,132.80 | PL-Box Type Waterproofing Basement Raft Box Type Waterproofing Basement Raft
| 1,461.820 | CUM | 1 | 17,24,947.60 | PL1298-Building 1-PL-ZC10 | 1,180.00 | PL-Box Type Waterproofing RW Raft & Wall Box Type Waterproofing RW Raft & Wall
PL-Pcc |  |  | 1 | 30,91,069.00 | PL-W-Pcc
| 523.910 | CUM | 1 | 30,91,069.00 | PL1298-Building 1-PL-ZC11 | 5,900.00 | PL-PCC below Footing, Lift Raft, Plinth Beam, Floor PCC, Retaining wall Raft, Basement Raft, Grade Slab - M15 PCC below Footing, Lift Raft, Plinth Beam, Floor PCC, Retaining wall Raft, Basement Raft, Grade Slab - M15
PL-Rmc-Conventional |  |  | 7 | 2,47,69,190.61 | PL-W-Rmc-Con
| 332.740 | CUM | 1 | 35,04,251.31 | PL1298-Building 1-PL-ZC12 | 10,531.50 | PL-Footing-M30 Footing-M30
| 799.920 | CUM | 1 | 84,24,357.48 | PL1298-Building 1-PL-ZC13 | 10,531.50 | PL-Lift Raft-M30 Lift Raft-M30
| 444.000 | CUM | 1 | 46,75,986.00 | PL1298-Building 1-PL-ZC14 | 10,531.50 | PL-Grade Slab-M30 Grade Slab-M30
| 243.800 | CUM | 1 | 25,67,579.70 | PL1298-Building 1-PL-ZC15 | 10,531.50 | PL-RW Raft-M30 RW Raft-M30
| 208.200 | CUM | 1 | 26,90,152.20 | PL1298-Building 1-PL-ZC16 | 12,921.00 | PL-RW Pardi-M30 RW Pardi-M30
| 143.590 | CUM | 1 | 20,84,065.26 | PL1298-Building 1-PL-ZC17 | 14,514.00 | PL-Column-M60 Column-M60
| 56.690 | CUM | 1 | 8,22,798.66 | PL1298-Building 1-PL-ZC18 | 14,514.00 | PL-Lift Wall-M60 Lift Wall-M60
PL-Reinforcement |  |  | 1 | 2,12,75,276.82 | PL-W-Reinf
| 271,853.780 | KGS | 1 | 2,12,75,276.82 | PL1298-Building 1-PL-ZC19 | 78.26 | PL-Reinforcement Steel Reinforcement Steel
BF-Rmc-Conventional |  |  | 8 | 2,07,42,189.86 | BF-W-Rmc-Con
| 143.590 | CUM | 1 | 20,84,065.26 | PL1298-Building 1--ZC20 | 14,514.00 | BF-Column-M60 Column-M60
| 56.690 | CUM | 1 | 8,22,798.66 | PL1298-Building 1--ZC21 | 14,514.00 | BF-Lift Wall-M60 Lift Wall-M60
| 208.200 | CUM | 1 | 26,90,152.20 | PL1298-Building 1--ZC22 | 12,921.00 | BF-RW Pardi-M30 RW Pardi-M30
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1--ZC23 | 13,688.00 | BF-PT Beam-M40 PT Beam-M40
| 960.000 | CUM | 1 | 1,31,40,480.00 | PL1298-Building 1--ZC24 | 13,688.00 | BF-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1--ZC25 | 12,862.00 | BF-RCC Beam-M30 RCC Beam-M30
| 43.110 | CUM | 1 | 5,54,480.82 | PL1298-Building 1--ZC26 | 12,862.00 | BF-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1--ZC27 | 12,862.00 | BF-Staircase-M30 Staircase-M30
BF-Reinforcement |  |  | 1 | 72,78,180.00 | BF-W-Reinf
| 93,000.000 | KGS | 1 | 72,78,180.00 | PL1298-Building 1--ZC28 | 78.26 | BF-Reinforcement Steel Reinforcement Steel
BF-PT Tendons |  |  | 1 | 22,51,601.66 | BF-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1--ZC29 | 165.20 | BF-PT Strand-Tendon PT Strand-Tendon
GF-Rmc-Conventional |  |  | 8 | 1,27,60,065.70 | GF-W-Rmc-Con
| 143.590 | CUM | 1 | 20,84,065.26 | PL1298-Building 1-GF-ZC30 | 14,514.00 | GF-Column-M60 Column-M60
| 56.690 | CUM | 1 | 8,22,798.66 | PL1298-Building 1-GF-ZC31 | 14,514.00 | GF-Lift Wall-M60 Lift Wall-M60
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1-GF-ZC32 | 13,688.00 | GF-PT Beam-M40 PT Beam-M40
| 565.850 | CUM | 1 | 77,45,354.80 | PL1298-Building 1-GF-ZC33 | 13,688.00 | GF-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-GF-ZC34 | 12,862.00 | GF-RCC Beam-M30 RCC Beam-M30
| 43.110 | CUM | 1 | 5,54,480.82 | PL1298-Building 1-GF-ZC35 | 12,862.00 | GF-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-GF-ZC36 | 12,862.00 | GF-Staircase-M30 Staircase-M30
| 8.020 | CUM | 1 | 1,03,153.24 | PL1298-Building 1-GF-ZC36A | 12,862.00 | GF-Parapet Wall-M35 Parapet Wall-M35
GF-Reinforcement |  |  | 1 | 74,46,512.56 | GF-W-Reinf
| 95,150.940 | KGS | 1 | 74,46,512.56 | PL1298-Building 1-GF-ZC37 | 78.26 | GF-Reinforcement Steel Reinforcement Steel
GF-PT Tendons |  |  | 1 | 22,51,601.66 | GF-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-GF-ZC38 | 165.20 | GF-PT Strand-Tendon PT Strand-Tendon
P1-Rmc-Conventional |  |  | 8 | 1,67,91,386.55 | P1-W-Rmc-Con
| 190.730 | CUM | 1 | 27,68,255.22 | PL1298-Building 1-P1-ZC39 | 14,514.00 | P1-Column-M60 Column-M60
| 92.840 | CUM | 1 | 13,47,479.76 | PL1298-Building 1-P1-ZC40 | 14,514.00 | P1-Lift Wall-M60 Lift Wall-M60
| 102.251 | CUM | 1 | 13,99,611.69 | PL1298-Building 1-P1-ZC41 | 13,688.00 | P1-PT Beam-M40 PT Beam-M40
| 683.560 | CUM | 1 | 93,56,569.28 | PL1298-Building 1-P1-ZC42 | 13,688.00 | P1-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-P1-ZC43 | 12,862.00 | P1-RCC Beam-M30 RCC Beam-M30
| 69.280 | CUM | 1 | 8,91,079.36 | PL1298-Building 1-P1-ZC44 | 12,862.00 | P1-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-P1-ZC45 | 12,862.00 | P1-Staircase-M30 Staircase-M30
| 32.200 | CUM | 1 | 4,67,350.80 | PL1298-Building 1-P1-ZC45A | 14,514.00 | P1-RCC Parapet Pardi-M35 RCC Parapet Pardi-M35
P1-Reinforcement |  |  | 1 | 1,26,25,963.62 | P1-W-Reinf
| 161,333.550 | KGS | 1 | 1,26,25,963.62 | PL1298-Building 1-P1-ZC46 | 78.26 | P1-Reinforcement Steel Reinforcement Steel
P1-PT Tendons |  |  | 1 | 22,51,601.66 | P1-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-P1-ZC47 | 165.20 | P1-PT Strand-Tendon PT Strand-Tendon
P2-Rmc-Conventional |  |  | 8 | 1,70,04,350.59 | P2-W-Rmc-Con
| 203.450 | CUM | 1 | 29,52,873.30 | PL1298-Building 1-P2-ZC48 | 14,514.00 | P2-Column-M60 Column-M60
| 99.020 | CUM | 1 | 14,37,176.28 | PL1298-Building 1-P2-ZC49 | 14,514.00 | P2-Lift Wall-M60 Lift Wall-M60
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-P2-ZC50 | 13,688.00 | P2-PT Beam-M40 PT Beam-M40
| 683.650 | CUM | 1 | 93,57,801.20 | PL1298-Building 1-P2-ZC51 | 13,688.00 | P2-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-P2-ZC52 | 12,862.00 | P2-RCC Beam-M30 RCC Beam-M30
| 69.280 | CUM | 1 | 8,91,079.36 | PL1298-Building 1-P2-ZC53 | 12,862.00 | P2-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-P2-ZC54 | 12,862.00 | P2-Staircase-M30 Staircase-M30
| 32.000 | CUM | 1 | 4,64,448.00 | PL1298-Building 1-P2-ZC55A | 14,514.00 | P2-RCC Parapet Pardi-M30 RCC Parapet Pardi-M35
P2-Reinforcement |  |  | 1 | 1,17,38,636.09 | P2-W-Reinf
| 149,995.350 | KGS | 1 | 1,17,38,636.09 | PL1298-Building 1-P2-ZC55 | 78.26 | P2-Reinforcement Steel Reinforcement Steel
P2-PT Tendons |  |  | 1 | 22,51,601.66 | P2-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-P2-ZC56 | 165.20 | P2-PT Strand-Tendon PT Strand-Tendon
P3-Rmc-Conventional |  |  | 8 | 1,67,47,430.96 | P3-W-Rmc-Con
| 203.450 | CUM | 1 | 29,52,873.30 | PL1298-Building 1-P3-ZC57 | 14,514.00 | P3-Column-M60 Column-M60
| 99.020 | CUM | 1 | 14,37,176.28 | PL1298-Building 1-P3-ZC58 | 14,514.00 | P3-Lift Wall-M60 Lift Wall-M60
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-P3-ZC59 | 13,688.00 | P3-PT Beam-M40 PT Beam-M40
| 683.560 | CUM | 1 | 93,56,569.28 | PL1298-Building 1-P3-ZC60 | 13,688.00 | P3-PT Slab-M40 PT Slab-M40
| 15.350 | CUM | 1 | 1,97,431.70 | PL1298-Building 1-P3-ZC61 | 12,862.00 | P3-RCC Beam-M30 RCC Beam-M30
| 69.280 | CUM | 1 | 8,91,079.36 | PL1298-Building 1-P3-ZC62 | 12,862.00 | P3-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-P3-ZC63 | 12,862.00 | P3-Staircase-M30 Staircase-M30
| 32.200 | CUM | 1 | 4,67,350.80 | PL1298-Building 1-P3-ZC64A | 14,514.00 | P3-RCC Parapet Paradi -M35 RCC Parapet Paradi -M35
P3-Reinforcement |  |  | 1 | 1,09,78,056.11 | P3-W-Reinf
| 140,276.720 | KGS | 1 | 1,09,78,056.11 | PL1298-Building 1-P3-ZC64 | 78.26 | P3-Reinforcement Steel Reinforcement Steel
P3-PT Tendons |  |  | 1 | 22,51,601.66 | P3-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-P3-ZC65 | 165.20 | P3-PT Strand-Tendon PT Strand-Tendon
P4-Rmc-Conventional |  |  | 7 | 1,26,56,912.46 | P4-W-Rmc-Con
| 143.590 | CUM | 1 | 20,84,065.26 | PL1298-Building 1-P4-ZC66 | 14,514.00 | P4-Column-M60 Column-M60
| 56.690 | CUM | 1 | 8,22,798.66 | PL1298-Building 1-P4-ZC67 | 14,514.00 | P4-Lift Wall-M60 Lift Wall-M60
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1-P4-ZC68 | 13,688.00 | P4-PT Beam-M40 PT Beam-M40
| 565.850 | CUM | 1 | 77,45,354.80 | PL1298-Building 1-P4-ZC69 | 13,688.00 | P4-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-P4-ZC70 | 12,862.00 | P4-RCC Beam-M30 RCC Beam-M30
| 43.110 | CUM | 1 | 5,54,480.82 | PL1298-Building 1-P4-ZC71 | 12,862.00 | P4-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-P4-ZC72 | 12,862.00 | P4-Staircase-M30 Staircase-M30
P4-Reinforcement |  |  | 1 | 74,46,512.56 | P4-W-Reinf
| 95,150.940 | KGS | 1 | 74,46,512.56 | PL1298-Building 1-P4-ZC73 | 78.26 | P4-Reinforcement Steel Reinforcement Steel
P4-PT Tendons |  |  | 1 | 22,51,601.66 | P4-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-P4-ZC74 | 165.20 | P4-PT Strand-Tendon PT Strand-Tendon
P5-Rmc-Conventional |  |  | 7 | 1,26,56,912.46 | P5-W-Rmc-Con
| 143.590 | CUM | 1 | 20,84,065.26 | PL1298-Building 1-P5-ZC75 | 14,514.00 | P5-Column-M60 Column-M60
| 56.690 | CUM | 1 | 8,22,798.66 | PL1298-Building 1-P5-ZC76 | 14,514.00 | P5-Lift Wall-M60 Lift Wall-M60
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1-P5-ZC77 | 13,688.00 | P5-PT Beam-M40 PT Beam-M40
| 565.850 | CUM | 1 | 77,45,354.80 | PL1298-Building 1-P5-ZC78 | 13,688.00 | P5-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-P5-ZC79 | 12,862.00 | P5-RCC Beam-M30 RCC Beam-M30
| 43.110 | CUM | 1 | 5,54,480.82 | PL1298-Building 1-P5-ZC80 | 12,862.00 | P5-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-P5-ZC81 | 12,862.00 | P5-Staircase-M30 Staircase-M30
P5-Reinforcement |  |  | 1 | 74,46,512.56 | P5-W-Reinf
| 95,150.940 | KGS | 1 | 74,46,512.56 | PL1298-Building 1-P5-ZC82 | 78.26 | P5-Reinforcement Steel Reinforcement Steel
P5-PT Tendons |  |  | 1 | 22,51,601.66 | P5-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-P5-ZC83 | 165.20 | P5-PT Strand-Tendon PT Strand-Tendon
F1-Rmc-Conventional |  |  | 7 | 1,45,15,866.29 | F1-W-Rmc-Con
| 139.870 | CUM | 1 | 19,72,306.87 | PL1298-Building 1-F1-ZC84 | 14,101.00 | F1-Column-M50 Column-M50
| 68.080 | CUM | 1 | 9,59,996.08 | PL1298-Building 1-F1-ZC85 | 14,101.00 | F1-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F1-ZC86 | 13,688.00 | F1-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F1-ZC87 | 13,688.00 | F1-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F1-ZC88 | 12,862.00 | F1-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F1-ZC89 | 12,862.00 | F1-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F1-ZC90 | 12,862.00 | F1-Staircase-M30 Staircase-M30
F1-Reinforcement |  |  | 1 | 1,00,96,348.43 | F1-W-Reinf
| 129,010.330 | KGS | 1 | 1,00,96,348.43 | PL1298-Building 1-F1-ZC91 | 78.26 | F1-Reinforcement Steel Reinforcement Steel
F1-PT Tendons |  |  | 1 | 22,51,601.66 | F1-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F1-ZC92 | 165.20 | F1-PT Strand-Tendon PT Strand-Tendon
F2-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F2-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F2-ZC93 | 14,101.00 | F2-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F2-ZC94 | 14,101.00 | F2-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F2-ZC95 | 13,688.00 | F2-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F2-ZC96 | 13,688.00 | F2-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F2-ZC97 | 12,862.00 | F2-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F2-ZC98 | 12,862.00 | F2-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F2-ZC99 | 12,862.00 | F2-Staircase-M30 Staircase-M30
F2-Reinforcement |  |  | 1 | 1,07,44,690.27 | F2-W-Reinf
| 137,294.790 | KGS | 1 | 1,07,44,690.27 | PL1298-Building 1-F2-ZC100 | 78.26 | F2-Reinforcement Steel Reinforcement Steel
F2-PT Tendons |  |  | 1 | 22,51,601.66 | F2-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F2-ZC101 | 165.20 | F2-PT Strand-Tendon PT Strand-Tendon
F3-Rmc-Conventional |  |  | 7 | 1,50,25,053.40 | F3-W-Rmc-Con
| 161.540 | CUM | 1 | 22,77,875.54 | PL1298-Building 1-F3-ZC102 | 14,101.00 | F3-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F3-ZC103 | 14,101.00 | F3-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F3-ZC104 | 13,688.00 | F3-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F3-ZC105 | 13,688.00 | F3-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F3-ZC106 | 12,862.00 | F3-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F3-ZC107 | 12,862.00 | F3-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F3-ZC108 | 12,862.00 | F3-Staircase-M30 Staircase-M30
F3-Reinforcement |  |  | 1 | 89,63,364.32 | F3-W-Reinf
| 114,533.150 | KGS | 1 | 89,63,364.32 | PL1298-Building 1-F3-ZC109 | 78.26 | F3-Reinforcement Steel Reinforcement Steel
F3-PT Tendons |  |  | 1 | 22,51,601.66 | F3-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F3-ZC110 | 165.20 | F3-PT Strand-Tendon PT Strand-Tendon
F4-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F4-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F4-ZC111 | 14,101.00 | F4-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F4-ZC112 | 14,101.00 | F4-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F4-ZC113 | 13,688.00 | F4-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F4-ZC114 | 13,688.00 | F4-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F4-ZC115 | 12,862.00 | F4-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F4-ZC116 | 12,862.00 | F4-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F4-ZC117 | 12,862.00 | F4-Staircase-M30 Staircase-M30
F4-Reinforcement |  |  | 1 | 89,39,473.11 | F4-W-Reinf
| 114,227.870 | KGS | 1 | 89,39,473.11 | PL1298-Building 1-F4-ZC118 | 78.26 | F4-Reinforcement Steel Reinforcement Steel
F4-PT Tendons |  |  | 1 | 22,51,601.66 | F4-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F4-ZC119 | 165.20 | F4-PT Strand-Tendon PT Strand-Tendon
F5-Rmc-Conventional |  |  | 7 | 1,38,40,851.42 | F5-W-Rmc-Con
| 87.140 | CUM | 1 | 12,28,761.14 | PL1298-Building 1-F5-ZC120 | 14,101.00 | F5-Column-M50 Column-M50
| 72.940 | CUM | 1 | 10,28,526.94 | PL1298-Building 1-F5-ZC121 | 14,101.00 | F5-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F5-ZC122 | 13,688.00 | F5-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F5-ZC123 | 13,688.00 | F5-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F5-ZC124 | 12,862.00 | F5-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F5-ZC125 | 12,862.00 | F5-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F5-ZC126 | 12,862.00 | F5-Staircase-M30 Staircase-M30
F5-Reinforcement |  |  | 1 | 89,39,473.11 | F5-W-Reinf
| 114,227.870 | KGS | 1 | 89,39,473.11 | PL1298-Building 1-F5-ZC127 | 78.26 | F5-Reinforcement Steel Reinforcement Steel
F5-PT Tendons |  |  | 1 | 22,51,601.66 | F5-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F5-ZC128 | 165.20 | F5-PT Strand-Tendon PT Strand-Tendon
F6-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F6-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F6-ZC129 | 14,101.00 | F6-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F6-ZC130 | 14,101.00 | F6-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F6-ZC131 | 13,688.00 | F6-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F6-ZC132 | 13,688.00 | F6-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F6-ZC133 | 12,862.00 | F6-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F6-ZC134 | 12,862.00 | F6-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F6-ZC135 | 12,862.00 | F6-Staircase-M30 Staircase-M30
F6-Reinforcement |  |  | 1 | 80,84,809.73 | F6-W-Reinf
| 103,307.050 | KGS | 1 | 80,84,809.73 | PL1298-Building 1-F6-ZC136 | 78.26 | F6-Reinforcement Steel Reinforcement Steel
F6-PT Tendons |  |  | 1 | 22,51,601.66 | F6-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F6-ZC137 | 165.20 | F6-PT Strand-Tendon PT Strand-Tendon
F7-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F7-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F7-ZC138 | 14,101.00 | F7-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F7-ZC139 | 14,101.00 | F7-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F7-ZC140 | 13,688.00 | F7-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F7-ZC141 | 13,688.00 | F7-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F7-ZC142 | 12,862.00 | F7-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F7-ZC143 | 12,862.00 | F7-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F7-ZC144 | 12,862.00 | F7-Staircase-M30 Staircase-M30
F7-Reinforcement |  |  | 1 | 80,95,597.87 | F7-W-Reinf
| 103,444.900 | KGS | 1 | 80,95,597.87 | PL1298-Building 1-F7-ZC145 | 78.26 | F7-Reinforcement Steel Reinforcement Steel
F7-PT Tendons |  |  | 1 | 22,51,601.66 | F7-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F7-ZC146 | 165.20 | F7-PT Strand-Tendon PT Strand-Tendon
F8-Rmc-Conventional |  |  | 7 | 1,25,82,680.43 | F8-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F8-ZC147 | 14,101.00 | F8-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F8-ZC148 | 14,101.00 | F8-Lift Wall-M50 Lift Wall-M50
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1-F8-ZC149 | 13,688.00 | F8-PT Beam-M40 PT Beam-M40
| 565.850 | CUM | 1 | 77,45,354.80 | PL1298-Building 1-F8-ZC150 | 13,688.00 | F8-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F8-ZC151 | 12,862.00 | F8-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F8-ZC152 | 12,862.00 | F8-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F8-ZC153 | 12,862.00 | F8-Staircase-M30 Staircase-M30
F8-Reinforcement |  |  | 1 | 80,85,828.68 | F8-W-Reinf
| 103,320.070 | KGS | 1 | 80,85,828.68 | PL1298-Building 1-F8-ZC154 | 78.26 | F8-Reinforcement Steel Reinforcement Steel
F8-PT Tendons |  |  | 1 | 22,51,601.66 | F8-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F8-ZC155 | 165.20 | F8-PT Strand-Tendon PT Strand-Tendon
F9-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F9-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F9-ZC156 | 14,101.00 | F9-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F9-ZC157 | 14,101.00 | F9-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F9-ZC158 | 13,688.00 | F9-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F9-ZC159 | 13,688.00 | F9-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F9-ZC160 | 12,862.00 | F9-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F9-ZC161 | 12,862.00 | F9-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F9-ZC162 | 12,862.00 | F9-Staircase-M30 Staircase-M30
F9-Reinforcement |  |  | 1 | 72,46,024.53 | F9-W-Reinf
| 92,589.120 | KGS | 1 | 72,46,024.53 | PL1298-Building 1-F9-ZC163 | 78.26 | F9-Reinforcement Steel Reinforcement Steel
F9-PT Tendons |  |  | 1 | 22,51,601.66 | F9-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F9-ZC164 | 165.20 | F9-PT Strand-Tendon PT Strand-Tendon
F10-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F10-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F10-ZC165 | 14,101.00 | F10-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F10-ZC166 | 14,101.00 | F10-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F10-ZC167 | 13,688.00 | F10-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F10-ZC168 | 13,688.00 | F10-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F10-ZC169 | 12,862.00 | F10-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F10-ZC170 | 12,862.00 | F10-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F10-ZC171 | 12,862.00 | F10-Staircase-M30 Staircase-M30
F10-Reinforcement |  |  | 1 | 72,60,389.15 | F10-W-Reinf
| 92,772.670 | KGS | 1 | 72,60,389.15 | PL1298-Building 1-F10-ZC172 | 78.26 | F10-Reinforcement Steel Reinforcement Steel
F10-PT Tendons |  |  | 1 | 22,51,601.66 | F10-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F10-ZC173 | 165.20 | F10-PT Strand-Tendon PT Strand-Tendon
F11-Rmc-Conventional |  |  | 7 | 1,48,05,077.80 | F11-W-Rmc-Con
| 145.940 | CUM | 1 | 20,57,899.94 | PL1298-Building 1-F11-ZC174 | 14,101.00 | F11-Column-M50 Column-M50
| 82.520 | CUM | 1 | 11,63,614.52 | PL1298-Building 1-F11-ZC175 | 14,101.00 | F11-Lift Wall-M50 Lift Wall-M50
| 97.891 | CUM | 1 | 13,39,932.01 | PL1298-Building 1-F11-ZC176 | 13,688.00 | F11-PT Beam-M40 PT Beam-M40
| 695.280 | CUM | 1 | 95,16,992.64 | PL1298-Building 1-F11-ZC177 | 13,688.00 | F11-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F11-ZC178 | 12,862.00 | F11-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F11-ZC179 | 12,862.00 | F11-RCC Slab-M30 RCC Slab-M30
| 8.165 | CUM | 1 | 1,05,018.23 | PL1298-Building 1-F11-ZC180 | 12,862.00 | F11-Staircase-M30 Staircase-M30
F11-Reinforcement |  |  | 1 | 74,46,512.56 | F11-W-Reinf
| 95,150.940 | KGS | 1 | 74,46,512.56 | PL1298-Building 1-F11-ZC181 | 78.26 | F11-Reinforcement Steel Reinforcement Steel
F11-PT Tendons |  |  | 1 | 22,51,601.66 | F11-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F11-ZC182 | 165.20 | F11-PT Strand-Tendon PT Strand-Tendon
TF-Rmc-Conventional |  |  | 8 | 1,23,73,646.38 | TF-W-Rmc-Con
| 87.140 | CUM | 1 | 12,28,761.14 | PL1298-Building 1-TF-ZC183 | 14,101.00 | TT-Column-M50 Column-M50
| 72.940 | CUM | 1 | 10,28,526.94 | PL1298-Building 1-TF-ZC184 | 14,101.00 | TT-Lift Wall-M50 Lift Wall-M50
| 64.960 | CUM | 1 | 8,89,172.48 | PL1298-Building 1-TF-ZC185 | 13,688.00 | TT-PT Beam-M40 PT Beam-M40
| 565.850 | CUM | 1 | 77,45,354.80 | PL1298-Building 1-TF-ZC186 | 13,688.00 | TT-PT Slab-M40 PT Slab-M40
| 30.390 | CUM | 1 | 3,90,876.18 | PL1298-Building 1-TF-ZC187 | 12,862.00 | TT-RCC Beam-M30 RCC Beam-M30
| 43.110 | CUM | 1 | 5,54,480.82 | PL1298-Building 1-TF-ZC188 | 12,862.00 | TT-RCC Slab-M30 RCC Slab-M30
| 13.230 | CUM | 1 | 1,70,164.26 | PL1298-Building 1-TF-ZC189 | 12,862.00 | TT-Staircase-M30 Staircase-M30
| 28.480 | CUM | 1 | 3,66,309.76 | PL1298-Building 1-TF-ZC189A | 12,862.00 | TT-Parapet-M35 Parapet-M35
TF-Reinforcement |  |  | 1 | 74,46,512.56 | TF-W-Reinf
| 95,150.940 | KGS | 1 | 74,46,512.56 | PL1298-Building 1-TF-ZC190 | 78.26 | TT-Reinforcement Steel Reinforcement Steel
TF-PT Tendons |  |  | 1 | 22,51,601.66 | TF-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-TF-ZC191 | 165.20 | TT-PT Strand-Tendon PT Strand-Tendon
AT-Rmc-Conventional |  |  | 2 | 22,57,288.08 | AT-W-Rmc-Con
| 87.140 | CUM | 1 | 12,28,761.14 | PL1298-Building 1-AT-ZC192 | 14,101.00 | AT-Column-M50 Column-M50
| 72.940 | CUM | 1 | 10,28,526.94 | PL1298-Building 1-AT-ZC193 | 14,101.00 | AT-Lift Wall-M50 Lift Wall-M50
AT-Reinforcement |  |  | 1 | 8,07,585.29 | AT-W-Reinf
| 10,319.260 | KGS | 1 | 8,07,585.29 | PL1298-Building 1-AT-ZC194 | 78.26 | AT-Reinforcement Steel Reinforcement Steel
ALL-Blockwork |  |  | 1 | 1,59,36,103.97 | ALL-W-Blockwork
| 11,730.230 | SQM | 1 | 1,59,36,103.97 | PL1298-Building 1-ALL-ZC195 | 1,358.55 | ALL-Block work Block work
ALL-Internal Plaster |  |  | 2 | 49,48,683.41 | ALL-W-Internal Plaster
| 1,361.260 | SQM | 1 | 8,27,237.70 | PL1298-Building 1-ALL-ZC196 | 607.70 | ALL-Ceiling Plaster Ceiling Plaster
| 6,782.040 | SQM | 1 | 41,21,445.71 | PL1298-Building 1-ALL-ZC197 | 607.70 | ALL-Internal Wall Plaster Internal Wall Plaster
ALL-External Plaster |  |  | 1 | 64,43,804.92 | ALL-W-External Plaster
| 7,974.710 | SQM | 1 | 64,43,804.92 | PL1298-Building 1-ALL-ZC198 | 808.03 | ALL-External Plaster External Plaster
ALL-Gypsum Plaster |  |  | 1 | 1,63,52,506.08 | ALL-W-Gypsum Plaster
| 38,494.600 | SQM | 1 | 1,63,52,506.08 | PL1298-Building 1-ALL-ZC199 | 424.80 | ALL-Gypsum Plaster Gypsum Plaster
ALL-Waterp |  |  | 9 | 95,79,864.67 | ALL-W-Waterp
| 2,895.100 | SQM | 1 | 32,79,569.28 | PL1298-Building 1-ALL-ZC200 | 1,132.80 | ALL-Box Type Waterproofing - Basement Raft, Stitch Raft Box Type Waterproofing - Basement Raft, Stitch Raft
| 224.090 | SQM | 1 | 2,64,426.20 | PL1298-Building 1-ALL-ZC201 | 1,180.00 | ALL-Box TypeWaterproofing - Lift Pit,R.W.Paradi Box TypeWaterproofing - Lift Pit,R.W.Paradi
| 478.010 | SQM | 1 | 9,52,062.08 | PL1298-Building 1-ALL-ZC202 | 1,991.72 | ALL-Brick Bat waterproofing+Chemical- Toilet-200MM Sunk Brick Bat waterproofing+Chemical-Toilet-200MM Sunk
| 601.010 | SQM | 1 | 10,86,956.64 | PL1298-Building 1-ALL-ZC203 | 1,808.55 | ALL-Brick Bat waterproofing+Chemical - Attached Terrace-150MM Sunk Brick Bat waterproofing+Chemical -Attached Terrace- 150MM Sunk
| 326.140 | SQM | 1 | 4,69,762.27 | PL1298-Building 1-ALL-ZC204 | 1,440.37 | ALL-Base Coat/Chemical Coat -Refuge Area-100MM Sunk Base Coat/Chemical Coat -Refuge Area-100MM Sunk
| 2,086.730 | SQM | 1 | 29,54,809.68 | PL1298-Building 1-ALL-ZC205 | 1,416.00 | ALL-Brick Bat Waterproofing+Chemical - Top terrace-250MM Sunk Brick Bat Waterproofing+Chemical -Top terrace-250MM Sunk
| 124.800 | SQM | 1 | 1,76,716.80 | PL1298-Building 1-ALL-ZC206 | 1,416.00 | ALL-Brick Bat Waterproofing-OHWT (Bottom) Brick Bat Waterproofing-OHWT (Bottom)
| 124.800 | SQM | 1 | 1,76,716.80 | PL1298-Building 1-ALL-ZC207 | 1,416.00 | ALL-Brick Bat Waterproofing with IPS Finish-LMR & OHWT (Top) Brick Bat Waterproofing with IPS Finish-LMR & OHWT (Top)
| 360.120 | SQM | 1 | 2,18,844.92 | PL1298-Building 1-ALL-ZC208 | 607.70 | ALL-Inside Waterproof plaster-OHWT Wall/Paradi (IPS Finish) Inside Waterproof plaster-OHWT Wall/Paradi (IPS Finish)
ALL-Doors |  |  | 1 | 86,57,945.95 | ALL-W-Doors
| 1.000 | NOS | 1 | 86,57,945.95 | PL1298-Building 1-ALL-ZC209 | 8,657,945.95 | ALL-Doors & Wooden Works Doors & Wooden Works
ALL-Sliding Windows |  |  | 1 | 81,48,655.01 | ALL-W-Sliding Windows
| 1.000 | NOS | 1 | 81,48,655.01 | PL1298-Building 1-ALL-ZC210 | 8,148,655.01 | ALL-Windows & Sliding Doors Windows & Sliding Doors
ALL-Flooring |  |  | 11 | 2,91,97,562.88 | ALL-W-Flooring
| 6,414.090 | SQM | 1 | 77,03,642.79 | PL1298-Building 1-ALL-ZC211 | 1,201.05 | ALL-Trimix- Ramp Area/Driveways Trimix- Ramp Area/Driveways
| 4,337.560 | SQM | 1 | 35,46,432.43 | PL1298-Building 1-ALL-ZC212 | 817.61 | ALL-PU Coating Paint - Basement- 1Parking& Podium-1,2&3 Parking PU Coating Paint - Basement-1Parking& Podium-1,2&3 Parking
| 326.140 | SQM | 1 | 3,37,522.29 | PL1298-Building 1-ALL-ZC213 | 1,034.90 | ALL-600 x 600 mm Vitrified Tile (Double Charge) -Refuge Area 600 x 600 mm Vitrified Tile (Double Charge) -Refuge Area
| 73.360 | SQM | 1 | 75,920.26 | PL1298-Building 1-ALL-ZC214 | 1,034.90 | ALL-Other room-/Driver room/Cafeteria- Vitrified 600x600 Other room-/Driver room/Cafeteria-Vitrified 600x600
| 482.430 | SQM | 1 | 4,49,069.97 | PL1298-Building 1-ALL-ZC215 | 930.85 | ALL-300 x 300 mm Antiskid Tiles - All Toilets 300 x 300 mm Antiskid Tiles - All Toilets
| 2,687.730 | SQM | 1 | 35,52,560.88 | PL1298-Building 1-ALL-ZC216 | 1,321.77 | ALL-600 X 600 mm Rustic Finish- common terrace & office terrace 600 X 600 mm Rustic Finish- common terrace & office terrace
| 2,171.100 | SQM | 1 | 96,58,789.68 | PL1298-Building 1-ALL-ZC217 | 4,448.80 | ALL-Premium Granite & Tile Combination - Floor Comman Lobby,Wide Passage etc Premium Granite & Tile Combination - Floor Comman Lobby,Wide Passage etc
| 196.240 | SQM | 1 | 16,04,279.66 | PL1298-Building 1-ALL-ZC218 | 8,175.09 | ALL-Designer Italian Marble - Main Entrance Lobby (East & West Side) (Granite + Tile Combination as per Interior) Designer Italian Marble - Main Entrance Lobby (East & West Side) (Granite + Tile Combination as per Interior)
| 458.020 | SQM | 1 | 8,21,417.65 | PL1298-Building 1-ALL-ZC219 | 1,793.41 | ALL-150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing 150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing
| 423.650 | SQM | 1 | 8,98,091.40 | PL1298-Building 1-ALL-ZC220 | 2,119.89 | ALL-Steel Grey Granite-Tread-300 mm wide Steel Grey Granite-Tread-300 mm wide
| 259.370 | SQM | 1 | 5,49,835.87 | PL1298-Building 1-ALL-ZC221 | 2,119.89 | ALL-Steel Grey Granite-Riser-150 mm height Steel Grey Granite-Riser-150 mm height
ALL-Skirting |  |  | 3 | 12,97,931.43 | ALL-W-Skirting
| 3,206.370 | RMT | 1 | 4,56,009.94 | PL1298-Building 1-ALL-ZC222 | 142.22 | ALL-Common lobby/Refuge Area/Driver room/Cafeteri-Vitrified 600x600 Common lobby/Refuge Area/Driver room/Cafeteri-Vitrified 600x600
| 575.350 | RMT | 1 | 5,89,405.80 | PL1298-Building 1-ALL-ZC223 | 1,024.43 | ALL-150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing 150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing
| 772.550 | RMT | 1 | 2,52,515.69 | PL1298-Building 1-ALL-ZC224 | 326.86 | ALL-Steel Grey Granite -Staircase- Tread Riser Steel Grey Granite -Staircase- Tread Riser
ALL-Dado |  |  | 2 | 38,14,499.99 | ALL-W-Dado
| 2,421.310 | SQM | 1 | 37,54,216.94 | PL1298-Building 1-ALL-ZC225 | 1,550.49 | ALL-300 X 600 mm Digital Ceramic Tile- Dado-Toilets-upto Lintel Ht. 300 X 600 mm Digital Ceramic Tile-Dado-Toilets-upto Lintel Ht.
| 38.880 | SQM | 1 | 60,283.05 | PL1298-Building 1-ALL-ZC226 | 1,550.49 | ALL-300 X 600 mm Digital Ceramic Tile- Kitchen/Pantry-Dado-(2Ft aboveKitchen Otta) 300 X 600 mm Digital Ceramic Tile-Kitchen/Pantry-Dado- (2Ft aboveKitchen Otta)
ALL-Granite & Stone Work |  |  | 10 | 73,26,797.11 | ALL-W-Granite & Stone Work
| 344.250 | SQM | 1 | 15,77,549.72 | PL1298-Building 1-ALL-ZC227 | 4,582.57 | ALL- Granite+Tile Combination as per interior design - Lift Cladding & Jams-Full Ht. Wall Cladding Cladding & Jams-Full Ht. Wall Cladding
| 264.730 | SQM | 1 | 24,93,836.02 | PL1298-Building 1-ALL-ZC228 | 9,420.30 | ALL-Italian Marble/Black Granite/Wall Paper -West & East Side Entrance Lobby -Full Ht. Wall Cladding Italian Marble/Black Granite/Wall Paper -West & East Side Entrance Lobby -Full Ht. Wall Cladding
| 29.160 | RMT | 1 | 1,47,147.78 | PL1298-Building 1-ALL-ZC229 | 5,046.22 | ALL-Granite with Black kadappa Matt Finish-Kitchen/Pantry Otta Granite with Black kadappa Matt Finish-Kitchen/Pantry Otta
| 43.490 | SQM | 1 | 3,04,326.06 | PL1298-Building 1-ALL-ZC230 | 6,997.61 | ALL-Black Granite-Washbasin Counter Black Granite-Washbasin Counter
| 151.950 | RMT | 1 | 71,156.67 | PL1298-Building 1-ALL-ZC231 | 468.29 | ALL-Granite & Ply Combination with laminate - Toilet Door Frame Granite & Ply Combination with laminate - Toilet Door Frame
| 1,361.700 | RMT | 1 | 17,62,775.12 | PL1298-Building 1-ALL-ZC232 | 1,294.54 | ALL-Black Granite Patti -@ Bund Wall- Below Glazing Black Granite Patti -@ Bund Wall-Below Glazing
| 63.550 | RMT | 1 | 38,195.46 | PL1298-Building 1-ALL-ZC233 | 601.03 | ALL-Black Granite Patti -@Office Attached Terrace - Door Frame Black Granite Patti -@Office Attached Terrace - Door Frame
| 466.020 | RMT | 1 | 2,09,750.94 | PL1298-Building 1-ALL-ZC234 | 450.09 | ALL-Steel Grey Granite - Ventilator Frame Steel Grey Granite - Ventilator Frame
| 588.820 | RMT | 1 | 2,65,021.99 | PL1298-Building 1-ALL-ZC235 | 450.09 | ALL-Steel Grey Granite - Window Bottom Patti Steel Grey Granite - Window Bottom Patti
| 353.050 | RMT | 1 | 4,57,037.35 | PL1298-Building 1-ALL-ZC236 | 1,294.54 | ALL-Black Granite Patti -@Toilet Ledge Wall Patti Black Granite Patti -@Toilet Ledge Wall Patti
ALL-Fabrication Work |  |  | 1 | 45,83,618.44 | ALL-W-Fabrication Work
| 1.000 | NOS | 1 | 45,83,618.44 | PL1298-Building 1-ALL-ZC237 | 4,583,618.44 | ALL-MS & SS Works- Grills & Railings MS & SS Works- Grills & Railings
ALL-Painting Work |  |  | 1 | 1,01,85,818.76 | ALL-W-Paint
| 1.000 | NOS | 1 | 1,01,85,818.76 | PL1298-Building 1-ALL-ZC238 | 10,185,818.76 | ALL-Painting & Polishing Works Painting & Polishing Works
ALL-Internal Plumbing |  |  | 1 | 56,55,000.00 | ALL-W-Plumb
| 1.000 | NOS | 1 | 56,55,000.00 | PL1298-Building 1-ALL-ZC239 | 5,655,000.00 | ALL-Plumbing work-3BHK Plumbing work-3BHK
ALL-Internal Electrical |  |  | 1 | 58,43,360.00 | ALL-W-Elect
| 1.000 | NOS | 1 | 58,43,360.00 | PL1298-Building 1-ALL-ZC240 | 5,843,360.00 | ALL-Electrical work-3BHK Electrical work-3BHK
ALL-Glazing & Facade Work |  |  | 1 | 10,87,33,615.31 | ALL-W-Glazing & Facade Work
| 1.000 | NOS | 1 | 10,87,33,615.31 | PL1298-Building 1-ALL-ZC241 | 108,733,615.31 | ALL-Elevation, Glazing, Facade Work Elevation, Glazing, Facade Work
ALL-Lift Work |  |  | 2 | 12,85,78,700.00 | ALL-W-Lift Work
| 6.000 | NOS | 1 | 12,51,03,600.00 | PL1298-Building 1-ALL-ZC242 | 20,850,600.00 | ALL-Lift 1-2.5X1.90 Lift 1-2.7X2.65
| 1.000 | NOS | 1 | 34,75,100.00 | PL1298-Building 1-ALL-ZC243 | 3,475,100.00 | ALL-Lift 2-1.90X1.90 Lift 2-2.4X3.0
ALL-Building Firefighting |  |  | 1 | 3,05,57,456.29 | ALL-W-Bldg Ff
| 1.000 | NOS | 1 | 3,05,57,456.29 | PL1298-Building 1-ALL-ZC244 | 30,557,456.29 | ALL-Buildings Fire Fighting Work Buildings Fire Fighting Work
ALL-Building Amenities |  |  | 1 | 3,13,21,392.70 | ALL-W-Amenities
| 1.000 | NOS | 1 | 3,13,21,392.70 | PL1298-Building 1-ALL-ZC245 | 31,321,392.70 | ALL-Bldg Amenities Bldg Amenities
ALL-Miscellaneous Work |  |  | 1 | 50,92,909.38 | ALL-W-Misc Work
| 1.000 | NOS | 1 | 50,92,909.38 | PL1298-Building 1-ALL-ZC246 | 5,092,909.38 | ALL-Misc, Dep. Labour, Cleaning Misc, Dep. Labour, Cleaning
F12-Rmc-Conventional |  |  | 7 | 1,43,46,581.01 | F12-W-Rmc-Con
| 127.700 | CUM | 1 | 18,00,697.70 | PL1298-Building 1-F12-ZC182.1 | 14,101.00 | F11-Column-M50 Column-M50
| 72.210 | CUM | 1 | 10,18,233.21 | PL1298-Building 1-F12-ZC182.2 | 14,101.00 | F11-Lift Wall-M50 Lift Wall-M50
| 97.890 | CUM | 1 | 13,39,918.32 | PL1298-Building 1-F12-ZC182.3 | 13,688.00 | F11-PT Beam-M40 PT Beam-M40
| 690.280 | CUM | 1 | 94,48,552.64 | PL1298-Building 1-F12-ZC182.4 | 13,688.00 | F11-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F12-ZC182.5 | 12,862.00 | F11-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F12-ZC182.6 | 12,862.00 | F11-RCC Slab-M30 RCC Slab-M30
| 9.140 | CUM | 1 | 1,17,558.68 | PL1298-Building 1-F12-ZC182.7 | 12,862.00 | F11-Staircase-M30 Staircase-M30
F12-Reinforcement |  |  | 1 | 76,88,899.44 | F12-W-Reinf
| 98,248.140 | KGS | 1 | 76,88,899.44 | PL1298-Building 1-F12-ZC182.8 | 78.26 | F11-Reinforcement Steel Reinforcement Steel
F12-PT Tendons |  |  | 1 | 22,51,601.66 | F12-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F12-ZC182.9 | 165.20 | F11-PT Strand-Tendon PT Strand-Tendon
F13-Rmc-Conventional |  |  | 7 | 1,43,46,581.01 | F13-W-Rmc-Con
| 127.700 | CUM | 1 | 18,00,697.70 | PL1298-Building 1-F13-ZC183.1 | 14,101.00 | F11-Column-M50 Column-M50
| 72.210 | CUM | 1 | 10,18,233.21 | PL1298-Building 1-F13-ZC183.2 | 14,101.00 | F11-Lift Wall-M50 Lift Wall-M50
| 97.890 | CUM | 1 | 13,39,918.32 | PL1298-Building 1-F13-ZC183.3 | 13,688.00 | F11-PT Beam-M40 PT Beam-M40
| 690.280 | CUM | 1 | 94,48,552.64 | PL1298-Building 1-F13-ZC183.4 | 13,688.00 | F11-PT Slab-M40 PT Slab-M40
| 23.400 | CUM | 1 | 3,00,970.80 | PL1298-Building 1-F13-ZC183.5 | 12,862.00 | F11-RCC Beam-M30 RCC Beam-M30
| 24.930 | CUM | 1 | 3,20,649.66 | PL1298-Building 1-F13-ZC183.6 | 12,862.00 | F11-RCC Slab-M30 RCC Slab-M30
| 9.140 | CUM | 1 | 1,17,558.68 | PL1298-Building 1-F13-ZC183.7 | 12,862.00 | F11-Staircase-M30 Staircase-M30
F13-Reinforcement |  |  | 1 | 76,88,899.44 | F13-W-Reinf
| 98,248.140 | KGS | 1 | 76,88,899.44 | PL1298-Building 1-F13-ZC183.8 | 78.26 | F11-Reinforcement Steel Reinforcement Steel
F13-PT Tendons |  |  | 1 | 22,51,601.66 | F13-W-Pt
| 13,629.550 | KGS | 1 | 22,51,601.66 | PL1298-Building 1-F13-ZC183.9 | 165.20 | F11-PT Strand-Tendon PT Strand-Tendon
OHWT-Rmc-Conventional |  |  | 4 | 44,46,191.03 | OHWT-W-Rmc-Con
| 38.640 | CUM | 1 | 5,44,862.64 | PL1298-Building 1--ZC252 | 14,101.00 | OHWT-Column-M40 Column-M40
| 90.210 | CUM | 1 | 12,72,051.21 | PL1298-Building 1--ZC253 | 14,101.00 | OHWT-Lift Wall-M40 Lift Wall-M40
| 98.600 | CUM | 1 | 13,49,636.80 | PL1298-Building 1--ZC254 | 13,688.00 | OHWT-PT Slab-M35 PT Slab-M35
| 6.740 | CUM | 1 | 86,689.88 | PL1298-Building 1--ZC255 | 12,862.00 | OHWT-RCC Beam-M35 RCC Beam-M35
| 92.750 | CUM | 0 | 11,92,950.50 | PL1298-Building 1-AT-ZC256 | 12,862.00 | RCC-OHWT Pardi-OHWT bottom slab to OHWT top slab-M-40 RCC-OHWT Pardi-OHWT bottom slab to OHWT top slab-M- 40
OHWT-Reinforcement |  |  | 1 | 19,94,647.84 | OHWT-W-Reinf
| 25,487.450 | KGS | 1 | 19,94,647.84 | PL1298-Building 1--ZC256 | 78.26 | OHWT-Reinforcement Steel Reinforcement Steel
Total |  |  | 274 | 1,05,92,80,436.3