## Report Info
Field | Value
Project Name | Zen Kode Building 1
Sub Project | All
Generated On | Mon Jun 22 12:27:49 IST 2026
Generated By | Rohit Ingale
Report Source | StrategicERP
Total Days | 274
Grand Total (INR) | 1059280436.3
Total Line Items | 246

## WBS Hierarchy
Level | WBS Name | WBS Code | Amount (INR) | Days | Parent
1 | Earthwork | W-Earthwork | 12563648.07 | 7
2 | Excavation | W-Excav | 9024279.65 | 3 | Earthwork
2 | Backfilling | W-Backfill | 1806221.99 | 2 | Earthwork
2 | Att | W-Att | 266944.51 | 1 | Earthwork
2 | Rubble-Soiling | W-Rub-Soil | 1466201.92 | 1 | Earthwork
1 | Rcc Work | W-Rcc Work | 597638133.35 | 212
2 | Pcc | W-Pcc | 3091069 | 1 | Rcc Work
2 | Rmc-Conventional | W-Rmc-Con | 341498722.84 | 166 | Rcc Work
2 | Reinforcement | W-Reinf | 205764706.65 | 24 | Rcc Work
2 | PT Tendons | W-Pt | 47283634.86 | 21 | Rcc Work
1 | Masonary & Plaster | W-Masonary & Plaster | 43681098.38 | 5
2 | Blockwork | W-Blockwork | 15936103.97 | 1 | Masonary & Plaster
2 | Internal Plaster | W-Internal Plaster | 4948683.41 | 2 | Masonary & Plaster
2 | External Plaster | W-External Plaster | 6443804.92 | 1 | Masonary & Plaster
2 | Gypsum Plaster | W-Gypsum Plaster | 16352506.08 | 1 | Masonary & Plaster
1 | Waterproofing | W-Waterproofing | 16402293.33 | 12
2 | Waterp | W-Waterp | 16402293.33 | 12 | Waterproofing
1 | Doors & Wooden Work | W-Doors & Wooden Work | 8657945.95 | 1
2 | Doors | W-Doors | 8657945.95 | 1 | Doors & Wooden Work
1 | Windows & Sliding Door | W-Windows & Sliding Door | 8148655.01 | 1
2 | Sliding Windows | W-Sliding Windows | 8148655.01 | 1 | Windows & Sliding Door
1 | Flooring & Tiling | W-Flooring & Tiling | 41636791.41 | 26
2 | Flooring | W-Flooring | 29197562.88 | 11 | Flooring & Tiling
2 | Skirting | W-Skirting | 1297931.43 | 3 | Flooring & Tiling
2 | Dado | W-Dado | 3814499.99 | 2 | Flooring & Tiling
1 | Granite & Stone Work | W-Granite & Stone Work | 7326797.11 | 10
1 | Ms & Ss Work | W-Ms & Ss Work | 4583618.44 | 1
2 | Fabrication Work | W-Fabrication Work | 4583618.44 | 1 | Ms & Ss Work
1 | Painting & Polishing Work | W-Painting & Polishing Work | 10185818.76 | 1
2 | Painting Work | W-Paint | 10185818.76 | 1 | Painting & Polishing Work
1 | Plumbing | W-Plumbing | 5655000 | 1
2 | Internal Plumbing | W-Plumb | 5655000 | 1 | Plumbing
1 | Electrical Work | W-Electrical Work | 5843360 | 1
2 | Internal Electrical | W-Elect | 5843360 | 1 | Electrical Work
1 | Lift | W-Lift | 128578700 | 2
2 | Lift Work | W-Lift Work | 128578700 | 2 | Lift
1 | Bldg. Firefighting | W-Bldg. Firefighting | 30557456.29 | 1
2 | Building Firefighting | W-Bldg Ff | 30557456.29 | 1 | Bldg. Firefighting
1 | Elevation,Glazing & Facade Work | W-Elevation,Glazing & Facade | 108733615.31 | 1
2 | Glazing & Facade Work | W-Glazing & Facade Work | 108733615.31 | 1 | Elevation,Glazing & Facade Work
1 | Bldg. Amenities | W-Bldg. Amenities | 31321392.7 | 1
2 | Building Amenities | W-Amenities | 31321392.7 | 1 | Bldg. Amenities
1 | Misc | W-Misc | 5092909.38 | 1
2 | Miscellaneous Work | W-Misc Work | 5092909.38 | 1 | Misc

## WBS Line Items
S.No | Group | Group Code | Group Amount (INR) | Activity Code | WBS Item Code | Amount (INR) | Qty | Unit | Unit Rate | Description | Long Description
1 | PL-Excavation | PL-W-Excav | 9024279.65 | ZC01 | PL1298-Building 1-PL-ZC01 | 1875175.67 | 13,242.766 | CUM | 141.6 | PL-Block Excavation Soft | Block Excavation Soft
2 | PL-Excavation | PL-W-Excav | 9024279.65 | ZC02 | PL1298-Building 1-PL-ZC02 | 3164357.5 | 9,932.070 | CUM | 318.6 | PL-Block Excavation Hard Murrum | Block Excavation Hard Murrum
3 | PL-Excavation | PL-W-Excav | 9024279.65 | ZC03 | PL1298-Building 1-PL-ZC03 | 3984746.48 | 9,932.070 | CUM | 401.2 | PL-Block Excavation Hard Rock | Block Excavation Hard Rock
4 | PL-Backfilling | PL-W-Backfill | 1806221.99 | ZC04 | PL1298-Building 1-PL-ZC04 | 754379.9 | 4,409.000 | CUM | 171.1 | PL-Backfilling From Excavated Material | Backfilling From Excavated Material
5 | PL-Backfilling | PL-W-Backfill | 1806221.99 | ZC05 | PL1298-Building 1-PL-ZC05 | 1051842.09 | 2,025.890 | CUM | 519.2 | PL-Murrum Filling Brought from out side (Inside The Plinth) | Murrum Filling Brought from out side (Inside The Plinth)
6 | PL-Att | PL-W-Att | 266944.51 | ZC06 | PL1298-Building 1-PL-ZC06 | 266944.51 | 3,376.480 | SQM | 79.06 | PL-Antitermite Treatment | Antitermite Treatment
7 | PL-Rubble-Soiling | PL-W-Rub-Soil | 1466201.92 | ZC07 | PL1298-Building 1-PL-ZC07 | 1466201.92 | 776.590 | CUM | 1888 | PL-Rubble Soiling | Rubble Soiling
8 | PL-Waterproofing | PL-W-Waterproofing | 6822428.66 | ZC08 | PL1298-Building 1-PL-ZC08 | 965570.4 | 818.280 | CUM | 1180 | PL-Box Type Waterproofing Lift | Box Type Waterproofing Lift
9 | PL-Waterproofing | PL-W-Waterproofing | 6822428.66 | ZC09 | PL1298-Building 1-PL-ZC09 | 4131910.66 | 3,647.520 | CUM | 1132.8 | PL-Box Type Waterproofing Basement Raft | Box Type Waterproofing Basement Raft
10 | PL-Waterproofing | PL-W-Waterproofing | 6822428.66 | ZC10 | PL1298-Building 1-PL-ZC10 | 1724947.6 | 1,461.820 | CUM | 1180 | PL-Box Type Waterproofing RW Raft & Wall | Box Type Waterproofing RW Raft & Wall
11 | PL-Pcc | PL-W-Pcc | 3091069 | ZC11 | PL1298-Building 1-PL-ZC11 | 3091069 | 523.910 | CUM | 5900 | PL-PCC below Footing, Lift Raft, Plinth Beam, Floor PCC, Retaining wall Raft, Basement Raft, Grade Slab - M15 | PCC below Footing, Lift Raft, Plinth Beam, Floor PCC, Retaining wall Raft, Basement Raft, Grade Slab - M15
12 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC12 | PL1298-Building 1-PL-ZC12 | 3504251.31 | 332.740 | CUM | 10531.5 | PL-Footing-M30 | Footing-M30
13 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC13 | PL1298-Building 1-PL-ZC13 | 8424357.48 | 799.920 | CUM | 10531.5 | PL-Lift Raft-M30 | Lift Raft-M30
14 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC14 | PL1298-Building 1-PL-ZC14 | 4675986 | 444.000 | CUM | 10531.5 | PL-Grade Slab-M30 | Grade Slab-M30
15 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC15 | PL1298-Building 1-PL-ZC15 | 2567579.7 | 243.800 | CUM | 10531.5 | PL-RW Raft-M30 | RW Raft-M30
16 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC16 | PL1298-Building 1-PL-ZC16 | 2690152.2 | 208.200 | CUM | 12921 | PL-RW Pardi-M30 | RW Pardi-M30
17 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC17 | PL1298-Building 1-PL-ZC17 | 2084065.26 | 143.590 | CUM | 14514 | PL-Column-M60 | Column-M60
18 | PL-Rmc-Conventional | PL-W-Rmc-Con | 24769190.61 | ZC18 | PL1298-Building 1-PL-ZC18 | 822798.66 | 56.690 | CUM | 14514 | PL-Lift Wall-M60 | Lift Wall-M60
19 | PL-Reinforcement | PL-W-Reinf | 21275276.82 | ZC19 | PL1298-Building 1-PL-ZC19 | 21275276.82 | 271,853.780 | KGS | 78.26 | PL-Reinforcement Steel | Reinforcement Steel
20 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC20 | PL1298-Building 1--ZC20 | 2084065.26 | 143.590 | CUM | 14514 | BF-Column-M60 | Column-M60
21 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC21 | PL1298-Building 1--ZC21 | 822798.66 | 56.690 | CUM | 14514 | BF-Lift Wall-M60 | Lift Wall-M60
22 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC22 | PL1298-Building 1--ZC22 | 2690152.2 | 208.200 | CUM | 12921 | BF-RW Pardi-M30 | RW Pardi-M30
23 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC23 | PL1298-Building 1--ZC23 | 889172.48 | 64.960 | CUM | 13688 | BF-PT Beam-M40 | PT Beam-M40
24 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC24 | PL1298-Building 1--ZC24 | 13140480 | 960.000 | CUM | 13688 | BF-PT Slab-M40 | PT Slab-M40
25 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC25 | PL1298-Building 1--ZC25 | 390876.18 | 30.390 | CUM | 12862 | BF-RCC Beam-M30 | RCC Beam-M30
26 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC26 | PL1298-Building 1--ZC26 | 554480.82 | 43.110 | CUM | 12862 | BF-RCC Slab-M30 | RCC Slab-M30
27 | BF-Rmc-Conventional | BF-W-Rmc-Con | 20742189.86 | ZC27 | PL1298-Building 1--ZC27 | 170164.26 | 13.230 | CUM | 12862 | BF-Staircase-M30 | Staircase-M30
28 | BF-Reinforcement | BF-W-Reinf | 7278180 | ZC28 | PL1298-Building 1--ZC28 | 7278180 | 93,000.000 | KGS | 78.26 | BF-Reinforcement Steel | Reinforcement Steel
29 | BF-PT Tendons | BF-W-Pt | 2251601.66 | ZC29 | PL1298-Building 1--ZC29 | 2251601.66 | 13,629.550 | KGS | 165.2 | BF-PT Strand-Tendon | PT Strand-Tendon
30 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC30 | PL1298-Building 1-GF-ZC30 | 2084065.26 | 143.590 | CUM | 14514 | GF-Column-M60 | Column-M60
31 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC31 | PL1298-Building 1-GF-ZC31 | 822798.66 | 56.690 | CUM | 14514 | GF-Lift Wall-M60 | Lift Wall-M60
32 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC32 | PL1298-Building 1-GF-ZC32 | 889172.48 | 64.960 | CUM | 13688 | GF-PT Beam-M40 | PT Beam-M40
33 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC33 | PL1298-Building 1-GF-ZC33 | 7745354.8 | 565.850 | CUM | 13688 | GF-PT Slab-M40 | PT Slab-M40
34 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC34 | PL1298-Building 1-GF-ZC34 | 390876.18 | 30.390 | CUM | 12862 | GF-RCC Beam-M30 | RCC Beam-M30
35 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC35 | PL1298-Building 1-GF-ZC35 | 554480.82 | 43.110 | CUM | 12862 | GF-RCC Slab-M30 | RCC Slab-M30
36 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC36 | PL1298-Building 1-GF-ZC36 | 170164.26 | 13.230 | CUM | 12862 | GF-Staircase-M30 | Staircase-M30
37 | GF-Rmc-Conventional | GF-W-Rmc-Con | 12760065.7 | ZC36A | PL1298-Building 1-GF-ZC36A | 103153.24 | 8.020 | CUM | 12862 | GF-Parapet Wall-M35 | Parapet Wall-M35
38 | GF-Reinforcement | GF-W-Reinf | 7446512.56 | ZC37 | PL1298-Building 1-GF-ZC37 | 7446512.56 | 95,150.940 | KGS | 78.26 | GF-Reinforcement Steel | Reinforcement Steel
39 | GF-PT Tendons | GF-W-Pt | 2251601.66 | ZC38 | PL1298-Building 1-GF-ZC38 | 2251601.66 | 13,629.550 | KGS | 165.2 | GF-PT Strand-Tendon | PT Strand-Tendon
40 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC39 | PL1298-Building 1-P1-ZC39 | 2768255.22 | 190.730 | CUM | 14514 | P1-Column-M60 | Column-M60
41 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC40 | PL1298-Building 1-P1-ZC40 | 1347479.76 | 92.840 | CUM | 14514 | P1-Lift Wall-M60 | Lift Wall-M60
42 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC41 | PL1298-Building 1-P1-ZC41 | 1399611.69 | 102.251 | CUM | 13688 | P1-PT Beam-M40 | PT Beam-M40
43 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC42 | PL1298-Building 1-P1-ZC42 | 9356569.28 | 683.560 | CUM | 13688 | P1-PT Slab-M40 | PT Slab-M40
44 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC43 | PL1298-Building 1-P1-ZC43 | 390876.18 | 30.390 | CUM | 12862 | P1-RCC Beam-M30 | RCC Beam-M30
45 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC44 | PL1298-Building 1-P1-ZC44 | 891079.36 | 69.280 | CUM | 12862 | P1-RCC Slab-M30 | RCC Slab-M30
46 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC45 | PL1298-Building 1-P1-ZC45 | 170164.26 | 13.230 | CUM | 12862 | P1-Staircase-M30 | Staircase-M30
47 | P1-Rmc-Conventional | P1-W-Rmc-Con | 16791386.55 | ZC45A | PL1298-Building 1-P1-ZC45A | 467350.8 | 32.200 | CUM | 14514 | P1-RCC Parapet Pardi-M35 | RCC Parapet Pardi-M35
48 | P1-Reinforcement | P1-W-Reinf | 12625963.62 | ZC46 | PL1298-Building 1-P1-ZC46 | 12625963.62 | 161,333.550 | KGS | 78.26 | P1-Reinforcement Steel | Reinforcement Steel
49 | P1-PT Tendons | P1-W-Pt | 2251601.66 | ZC47 | PL1298-Building 1-P1-ZC47 | 2251601.66 | 13,629.550 | KGS | 165.2 | P1-PT Strand-Tendon | PT Strand-Tendon
50 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC48 | PL1298-Building 1-P2-ZC48 | 2952873.3 | 203.450 | CUM | 14514 | P2-Column-M60 | Column-M60
51 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC49 | PL1298-Building 1-P2-ZC49 | 1437176.28 | 99.020 | CUM | 14514 | P2-Lift Wall-M60 | Lift Wall-M60
52 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC50 | PL1298-Building 1-P2-ZC50 | 1339932.01 | 97.891 | CUM | 13688 | P2-PT Beam-M40 | PT Beam-M40
53 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC51 | PL1298-Building 1-P2-ZC51 | 9357801.2 | 683.650 | CUM | 13688 | P2-PT Slab-M40 | PT Slab-M40
54 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC52 | PL1298-Building 1-P2-ZC52 | 390876.18 | 30.390 | CUM | 12862 | P2-RCC Beam-M30 | RCC Beam-M30
55 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC53 | PL1298-Building 1-P2-ZC53 | 891079.36 | 69.280 | CUM | 12862 | P2-RCC Slab-M30 | RCC Slab-M30
56 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC54 | PL1298-Building 1-P2-ZC54 | 170164.26 | 13.230 | CUM | 12862 | P2-Staircase-M30 | Staircase-M30
57 | P2-Rmc-Conventional | P2-W-Rmc-Con | 17004350.59 | ZC55A | PL1298-Building 1-P2-ZC55A | 464448 | 32.000 | CUM | 14514 | P2-RCC Parapet Pardi-M30 | RCC Parapet Pardi-M35
58 | P2-Reinforcement | P2-W-Reinf | 11738636.09 | ZC55 | PL1298-Building 1-P2-ZC55 | 11738636.09 | 149,995.350 | KGS | 78.26 | P2-Reinforcement Steel | Reinforcement Steel
59 | P2-PT Tendons | P2-W-Pt | 2251601.66 | ZC56 | PL1298-Building 1-P2-ZC56 | 2251601.66 | 13,629.550 | KGS | 165.2 | P2-PT Strand-Tendon | PT Strand-Tendon
60 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC57 | PL1298-Building 1-P3-ZC57 | 2952873.3 | 203.450 | CUM | 14514 | P3-Column-M60 | Column-M60
61 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC58 | PL1298-Building 1-P3-ZC58 | 1437176.28 | 99.020 | CUM | 14514 | P3-Lift Wall-M60 | Lift Wall-M60
62 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC59 | PL1298-Building 1-P3-ZC59 | 1339932.01 | 97.891 | CUM | 13688 | P3-PT Beam-M40 | PT Beam-M40
63 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC60 | PL1298-Building 1-P3-ZC60 | 9356569.28 | 683.560 | CUM | 13688 | P3-PT Slab-M40 | PT Slab-M40
64 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC61 | PL1298-Building 1-P3-ZC61 | 197431.7 | 15.350 | CUM | 12862 | P3-RCC Beam-M30 | RCC Beam-M30
65 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC62 | PL1298-Building 1-P3-ZC62 | 891079.36 | 69.280 | CUM | 12862 | P3-RCC Slab-M30 | RCC Slab-M30
66 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC63 | PL1298-Building 1-P3-ZC63 | 105018.23 | 8.165 | CUM | 12862 | P3-Staircase-M30 | Staircase-M30
67 | P3-Rmc-Conventional | P3-W-Rmc-Con | 16747430.96 | ZC64A | PL1298-Building 1-P3-ZC64A | 467350.8 | 32.200 | CUM | 14514 | P3-RCC Parapet Paradi -M35 | RCC Parapet Paradi -M35
68 | P3-Reinforcement | P3-W-Reinf | 10978056.11 | ZC64 | PL1298-Building 1-P3-ZC64 | 10978056.11 | 140,276.720 | KGS | 78.26 | P3-Reinforcement Steel | Reinforcement Steel
69 | P3-PT Tendons | P3-W-Pt | 2251601.66 | ZC65 | PL1298-Building 1-P3-ZC65 | 2251601.66 | 13,629.550 | KGS | 165.2 | P3-PT Strand-Tendon | PT Strand-Tendon
70 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC66 | PL1298-Building 1-P4-ZC66 | 2084065.26 | 143.590 | CUM | 14514 | P4-Column-M60 | Column-M60
71 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC67 | PL1298-Building 1-P4-ZC67 | 822798.66 | 56.690 | CUM | 14514 | P4-Lift Wall-M60 | Lift Wall-M60
72 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC68 | PL1298-Building 1-P4-ZC68 | 889172.48 | 64.960 | CUM | 13688 | P4-PT Beam-M40 | PT Beam-M40
73 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC69 | PL1298-Building 1-P4-ZC69 | 7745354.8 | 565.850 | CUM | 13688 | P4-PT Slab-M40 | PT Slab-M40
74 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC70 | PL1298-Building 1-P4-ZC70 | 390876.18 | 30.390 | CUM | 12862 | P4-RCC Beam-M30 | RCC Beam-M30
75 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC71 | PL1298-Building 1-P4-ZC71 | 554480.82 | 43.110 | CUM | 12862 | P4-RCC Slab-M30 | RCC Slab-M30
76 | P4-Rmc-Conventional | P4-W-Rmc-Con | 12656912.46 | ZC72 | PL1298-Building 1-P4-ZC72 | 170164.26 | 13.230 | CUM | 12862 | P4-Staircase-M30 | Staircase-M30
77 | P4-Reinforcement | P4-W-Reinf | 7446512.56 | ZC73 | PL1298-Building 1-P4-ZC73 | 7446512.56 | 95,150.940 | KGS | 78.26 | P4-Reinforcement Steel | Reinforcement Steel
78 | P4-PT Tendons | P4-W-Pt | 2251601.66 | ZC74 | PL1298-Building 1-P4-ZC74 | 2251601.66 | 13,629.550 | KGS | 165.2 | P4-PT Strand-Tendon | PT Strand-Tendon
79 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC75 | PL1298-Building 1-P5-ZC75 | 2084065.26 | 143.590 | CUM | 14514 | P5-Column-M60 | Column-M60
80 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC76 | PL1298-Building 1-P5-ZC76 | 822798.66 | 56.690 | CUM | 14514 | P5-Lift Wall-M60 | Lift Wall-M60
81 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC77 | PL1298-Building 1-P5-ZC77 | 889172.48 | 64.960 | CUM | 13688 | P5-PT Beam-M40 | PT Beam-M40
82 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC78 | PL1298-Building 1-P5-ZC78 | 7745354.8 | 565.850 | CUM | 13688 | P5-PT Slab-M40 | PT Slab-M40
83 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC79 | PL1298-Building 1-P5-ZC79 | 390876.18 | 30.390 | CUM | 12862 | P5-RCC Beam-M30 | RCC Beam-M30
84 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC80 | PL1298-Building 1-P5-ZC80 | 554480.82 | 43.110 | CUM | 12862 | P5-RCC Slab-M30 | RCC Slab-M30
85 | P5-Rmc-Conventional | P5-W-Rmc-Con | 12656912.46 | ZC81 | PL1298-Building 1-P5-ZC81 | 170164.26 | 13.230 | CUM | 12862 | P5-Staircase-M30 | Staircase-M30
86 | P5-Reinforcement | P5-W-Reinf | 7446512.56 | ZC82 | PL1298-Building 1-P5-ZC82 | 7446512.56 | 95,150.940 | KGS | 78.26 | P5-Reinforcement Steel | Reinforcement Steel
87 | P5-PT Tendons | P5-W-Pt | 2251601.66 | ZC83 | PL1298-Building 1-P5-ZC83 | 2251601.66 | 13,629.550 | KGS | 165.2 | P5-PT Strand-Tendon | PT Strand-Tendon
88 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC84 | PL1298-Building 1-F1-ZC84 | 1972306.87 | 139.870 | CUM | 14101 | F1-Column-M50 | Column-M50
89 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC85 | PL1298-Building 1-F1-ZC85 | 959996.08 | 68.080 | CUM | 14101 | F1-Lift Wall-M50 | Lift Wall-M50
90 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC86 | PL1298-Building 1-F1-ZC86 | 1339932.01 | 97.891 | CUM | 13688 | F1-PT Beam-M40 | PT Beam-M40
91 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC87 | PL1298-Building 1-F1-ZC87 | 9516992.64 | 695.280 | CUM | 13688 | F1-PT Slab-M40 | PT Slab-M40
92 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC88 | PL1298-Building 1-F1-ZC88 | 300970.8 | 23.400 | CUM | 12862 | F1-RCC Beam-M30 | RCC Beam-M30
93 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC89 | PL1298-Building 1-F1-ZC89 | 320649.66 | 24.930 | CUM | 12862 | F1-RCC Slab-M30 | RCC Slab-M30
94 | F1-Rmc-Conventional | F1-W-Rmc-Con | 14515866.29 | ZC90 | PL1298-Building 1-F1-ZC90 | 105018.23 | 8.165 | CUM | 12862 | F1-Staircase-M30 | Staircase-M30
95 | F1-Reinforcement | F1-W-Reinf | 10096348.43 | ZC91 | PL1298-Building 1-F1-ZC91 | 10096348.43 | 129,010.330 | KGS | 78.26 | F1-Reinforcement Steel | Reinforcement Steel
96 | F1-PT Tendons | F1-W-Pt | 2251601.66 | ZC92 | PL1298-Building 1-F1-ZC92 | 2251601.66 | 13,629.550 | KGS | 165.2 | F1-PT Strand-Tendon | PT Strand-Tendon
97 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC93 | PL1298-Building 1-F2-ZC93 | 2057899.94 | 145.940 | CUM | 14101 | F2-Column-M50 | Column-M50
98 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC94 | PL1298-Building 1-F2-ZC94 | 1163614.52 | 82.520 | CUM | 14101 | F2-Lift Wall-M50 | Lift Wall-M50
99 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC95 | PL1298-Building 1-F2-ZC95 | 1339932.01 | 97.891 | CUM | 13688 | F2-PT Beam-M40 | PT Beam-M40
100 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC96 | PL1298-Building 1-F2-ZC96 | 9516992.64 | 695.280 | CUM | 13688 | F2-PT Slab-M40 | PT Slab-M40
101 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC97 | PL1298-Building 1-F2-ZC97 | 300970.8 | 23.400 | CUM | 12862 | F2-RCC Beam-M30 | RCC Beam-M30
102 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC98 | PL1298-Building 1-F2-ZC98 | 320649.66 | 24.930 | CUM | 12862 | F2-RCC Slab-M30 | RCC Slab-M30
103 | F2-Rmc-Conventional | F2-W-Rmc-Con | 14805077.8 | ZC99 | PL1298-Building 1-F2-ZC99 | 105018.23 | 8.165 | CUM | 12862 | F2-Staircase-M30 | Staircase-M30
104 | F2-Reinforcement | F2-W-Reinf | 10744690.27 | ZC100 | PL1298-Building 1-F2-ZC100 | 10744690.27 | 137,294.790 | KGS | 78.26 | F2-Reinforcement Steel | Reinforcement Steel
105 | F2-PT Tendons | F2-W-Pt | 2251601.66 | ZC101 | PL1298-Building 1-F2-ZC101 | 2251601.66 | 13,629.550 | KGS | 165.2 | F2-PT Strand-Tendon | PT Strand-Tendon
106 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC102 | PL1298-Building 1-F3-ZC102 | 2277875.54 | 161.540 | CUM | 14101 | F3-Column-M50 | Column-M50
107 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC103 | PL1298-Building 1-F3-ZC103 | 1163614.52 | 82.520 | CUM | 14101 | F3-Lift Wall-M50 | Lift Wall-M50
108 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC104 | PL1298-Building 1-F3-ZC104 | 1339932.01 | 97.891 | CUM | 13688 | F3-PT Beam-M40 | PT Beam-M40
109 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC105 | PL1298-Building 1-F3-ZC105 | 9516992.64 | 695.280 | CUM | 13688 | F3-PT Slab-M40 | PT Slab-M40
110 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC106 | PL1298-Building 1-F3-ZC106 | 300970.8 | 23.400 | CUM | 12862 | F3-RCC Beam-M30 | RCC Beam-M30
111 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC107 | PL1298-Building 1-F3-ZC107 | 320649.66 | 24.930 | CUM | 12862 | F3-RCC Slab-M30 | RCC Slab-M30
112 | F3-Rmc-Conventional | F3-W-Rmc-Con | 15025053.4 | ZC108 | PL1298-Building 1-F3-ZC108 | 105018.23 | 8.165 | CUM | 12862 | F3-Staircase-M30 | Staircase-M30
113 | F3-Reinforcement | F3-W-Reinf | 8963364.32 | ZC109 | PL1298-Building 1-F3-ZC109 | 8963364.32 | 114,533.150 | KGS | 78.26 | F3-Reinforcement Steel | Reinforcement Steel
114 | F3-PT Tendons | F3-W-Pt | 2251601.66 | ZC110 | PL1298-Building 1-F3-ZC110 | 2251601.66 | 13,629.550 | KGS | 165.2 | F3-PT Strand-Tendon | PT Strand-Tendon
115 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC111 | PL1298-Building 1-F4-ZC111 | 2057899.94 | 145.940 | CUM | 14101 | F4-Column-M50 | Column-M50
116 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC112 | PL1298-Building 1-F4-ZC112 | 1163614.52 | 82.520 | CUM | 14101 | F4-Lift Wall-M50 | Lift Wall-M50
117 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC113 | PL1298-Building 1-F4-ZC113 | 1339932.01 | 97.891 | CUM | 13688 | F4-PT Beam-M40 | PT Beam-M40
118 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC114 | PL1298-Building 1-F4-ZC114 | 9516992.64 | 695.280 | CUM | 13688 | F4-PT Slab-M40 | PT Slab-M40
119 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC115 | PL1298-Building 1-F4-ZC115 | 300970.8 | 23.400 | CUM | 12862 | F4-RCC Beam-M30 | RCC Beam-M30
120 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC116 | PL1298-Building 1-F4-ZC116 | 320649.66 | 24.930 | CUM | 12862 | F4-RCC Slab-M30 | RCC Slab-M30
121 | F4-Rmc-Conventional | F4-W-Rmc-Con | 14805077.8 | ZC117 | PL1298-Building 1-F4-ZC117 | 105018.23 | 8.165 | CUM | 12862 | F4-Staircase-M30 | Staircase-M30
122 | F4-Reinforcement | F4-W-Reinf | 8939473.11 | ZC118 | PL1298-Building 1-F4-ZC118 | 8939473.11 | 114,227.870 | KGS | 78.26 | F4-Reinforcement Steel | Reinforcement Steel
123 | F4-PT Tendons | F4-W-Pt | 2251601.66 | ZC119 | PL1298-Building 1-F4-ZC119 | 2251601.66 | 13,629.550 | KGS | 165.2 | F4-PT Strand-Tendon | PT Strand-Tendon
124 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC120 | PL1298-Building 1-F5-ZC120 | 1228761.14 | 87.140 | CUM | 14101 | F5-Column-M50 | Column-M50
125 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC121 | PL1298-Building 1-F5-ZC121 | 1028526.94 | 72.940 | CUM | 14101 | F5-Lift Wall-M50 | Lift Wall-M50
126 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC122 | PL1298-Building 1-F5-ZC122 | 1339932.01 | 97.891 | CUM | 13688 | F5-PT Beam-M40 | PT Beam-M40
127 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC123 | PL1298-Building 1-F5-ZC123 | 9516992.64 | 695.280 | CUM | 13688 | F5-PT Slab-M40 | PT Slab-M40
128 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC124 | PL1298-Building 1-F5-ZC124 | 300970.8 | 23.400 | CUM | 12862 | F5-RCC Beam-M30 | RCC Beam-M30
129 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC125 | PL1298-Building 1-F5-ZC125 | 320649.66 | 24.930 | CUM | 12862 | F5-RCC Slab-M30 | RCC Slab-M30
130 | F5-Rmc-Conventional | F5-W-Rmc-Con | 13840851.42 | ZC126 | PL1298-Building 1-F5-ZC126 | 105018.23 | 8.165 | CUM | 12862 | F5-Staircase-M30 | Staircase-M30
131 | F5-Reinforcement | F5-W-Reinf | 8939473.11 | ZC127 | PL1298-Building 1-F5-ZC127 | 8939473.11 | 114,227.870 | KGS | 78.26 | F5-Reinforcement Steel | Reinforcement Steel
132 | F5-PT Tendons | F5-W-Pt | 2251601.66 | ZC128 | PL1298-Building 1-F5-ZC128 | 2251601.66 | 13,629.550 | KGS | 165.2 | F5-PT Strand-Tendon | PT Strand-Tendon
133 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC129 | PL1298-Building 1-F6-ZC129 | 2057899.94 | 145.940 | CUM | 14101 | F6-Column-M50 | Column-M50
134 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC130 | PL1298-Building 1-F6-ZC130 | 1163614.52 | 82.520 | CUM | 14101 | F6-Lift Wall-M50 | Lift Wall-M50
135 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC131 | PL1298-Building 1-F6-ZC131 | 1339932.01 | 97.891 | CUM | 13688 | F6-PT Beam-M40 | PT Beam-M40
136 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC132 | PL1298-Building 1-F6-ZC132 | 9516992.64 | 695.280 | CUM | 13688 | F6-PT Slab-M40 | PT Slab-M40
137 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC133 | PL1298-Building 1-F6-ZC133 | 300970.8 | 23.400 | CUM | 12862 | F6-RCC Beam-M30 | RCC Beam-M30
138 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC134 | PL1298-Building 1-F6-ZC134 | 320649.66 | 24.930 | CUM | 12862 | F6-RCC Slab-M30 | RCC Slab-M30
139 | F6-Rmc-Conventional | F6-W-Rmc-Con | 14805077.8 | ZC135 | PL1298-Building 1-F6-ZC135 | 105018.23 | 8.165 | CUM | 12862 | F6-Staircase-M30 | Staircase-M30
140 | F6-Reinforcement | F6-W-Reinf | 8084809.73 | ZC136 | PL1298-Building 1-F6-ZC136 | 8084809.73 | 103,307.050 | KGS | 78.26 | F6-Reinforcement Steel | Reinforcement Steel
141 | F6-PT Tendons | F6-W-Pt | 2251601.66 | ZC137 | PL1298-Building 1-F6-ZC137 | 2251601.66 | 13,629.550 | KGS | 165.2 | F6-PT Strand-Tendon | PT Strand-Tendon
142 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC138 | PL1298-Building 1-F7-ZC138 | 2057899.94 | 145.940 | CUM | 14101 | F7-Column-M50 | Column-M50
143 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC139 | PL1298-Building 1-F7-ZC139 | 1163614.52 | 82.520 | CUM | 14101 | F7-Lift Wall-M50 | Lift Wall-M50
144 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC140 | PL1298-Building 1-F7-ZC140 | 1339932.01 | 97.891 | CUM | 13688 | F7-PT Beam-M40 | PT Beam-M40
145 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC141 | PL1298-Building 1-F7-ZC141 | 9516992.64 | 695.280 | CUM | 13688 | F7-PT Slab-M40 | PT Slab-M40
146 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC142 | PL1298-Building 1-F7-ZC142 | 300970.8 | 23.400 | CUM | 12862 | F7-RCC Beam-M30 | RCC Beam-M30
147 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC143 | PL1298-Building 1-F7-ZC143 | 320649.66 | 24.930 | CUM | 12862 | F7-RCC Slab-M30 | RCC Slab-M30
148 | F7-Rmc-Conventional | F7-W-Rmc-Con | 14805077.8 | ZC144 | PL1298-Building 1-F7-ZC144 | 105018.23 | 8.165 | CUM | 12862 | F7-Staircase-M30 | Staircase-M30
149 | F7-Reinforcement | F7-W-Reinf | 8095597.87 | ZC145 | PL1298-Building 1-F7-ZC145 | 8095597.87 | 103,444.900 | KGS | 78.26 | F7-Reinforcement Steel | Reinforcement Steel
150 | F7-PT Tendons | F7-W-Pt | 2251601.66 | ZC146 | PL1298-Building 1-F7-ZC146 | 2251601.66 | 13,629.550 | KGS | 165.2 | F7-PT Strand-Tendon | PT Strand-Tendon
151 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC147 | PL1298-Building 1-F8-ZC147 | 2057899.94 | 145.940 | CUM | 14101 | F8-Column-M50 | Column-M50
152 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC148 | PL1298-Building 1-F8-ZC148 | 1163614.52 | 82.520 | CUM | 14101 | F8-Lift Wall-M50 | Lift Wall-M50
153 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC149 | PL1298-Building 1-F8-ZC149 | 889172.48 | 64.960 | CUM | 13688 | F8-PT Beam-M40 | PT Beam-M40
154 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC150 | PL1298-Building 1-F8-ZC150 | 7745354.8 | 565.850 | CUM | 13688 | F8-PT Slab-M40 | PT Slab-M40
155 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC151 | PL1298-Building 1-F8-ZC151 | 300970.8 | 23.400 | CUM | 12862 | F8-RCC Beam-M30 | RCC Beam-M30
156 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC152 | PL1298-Building 1-F8-ZC152 | 320649.66 | 24.930 | CUM | 12862 | F8-RCC Slab-M30 | RCC Slab-M30
157 | F8-Rmc-Conventional | F8-W-Rmc-Con | 12582680.43 | ZC153 | PL1298-Building 1-F8-ZC153 | 105018.23 | 8.165 | CUM | 12862 | F8-Staircase-M30 | Staircase-M30
158 | F8-Reinforcement | F8-W-Reinf | 8085828.68 | ZC154 | PL1298-Building 1-F8-ZC154 | 8085828.68 | 103,320.070 | KGS | 78.26 | F8-Reinforcement Steel | Reinforcement Steel
159 | F8-PT Tendons | F8-W-Pt | 2251601.66 | ZC155 | PL1298-Building 1-F8-ZC155 | 2251601.66 | 13,629.550 | KGS | 165.2 | F8-PT Strand-Tendon | PT Strand-Tendon
160 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC156 | PL1298-Building 1-F9-ZC156 | 2057899.94 | 145.940 | CUM | 14101 | F9-Column-M50 | Column-M50
161 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC157 | PL1298-Building 1-F9-ZC157 | 1163614.52 | 82.520 | CUM | 14101 | F9-Lift Wall-M50 Lift Wall-M50 Page 10 | of Report By StrategicERP 17
162 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC158 | PL1298-Building 1-F9-ZC158 | 1339932.01 | 97.891 | CUM | 13688 | F9-PT Beam-M40 | PT Beam-M40
163 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC159 | PL1298-Building 1-F9-ZC159 | 9516992.64 | 695.280 | CUM | 13688 | F9-PT Slab-M40 | PT Slab-M40
164 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC160 | PL1298-Building 1-F9-ZC160 | 300970.8 | 23.400 | CUM | 12862 | F9-RCC Beam-M30 | RCC Beam-M30
165 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC161 | PL1298-Building 1-F9-ZC161 | 320649.66 | 24.930 | CUM | 12862 | F9-RCC Slab-M30 | RCC Slab-M30
166 | F9-Rmc-Conventional | F9-W-Rmc-Con | 14805077.8 | ZC162 | PL1298-Building 1-F9-ZC162 | 105018.23 | 8.165 | CUM | 12862 | F9-Staircase-M30 | Staircase-M30
167 | F9-Reinforcement | F9-W-Reinf | 7246024.53 | ZC163 | PL1298-Building 1-F9-ZC163 | 7246024.53 | 92,589.120 | KGS | 78.26 | F9-Reinforcement Steel | Reinforcement Steel
168 | F9-PT Tendons | F9-W-Pt | 2251601.66 | ZC164 | PL1298-Building 1-F9-ZC164 | 2251601.66 | 13,629.550 | KGS | 165.2 | F9-PT Strand-Tendon | PT Strand-Tendon
169 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC165 | PL1298-Building 1-F10-ZC165 | 2057899.94 | 145.940 | CUM | 14101 | F10-Column-M50 | Column-M50
170 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC166 | PL1298-Building 1-F10-ZC166 | 1163614.52 | 82.520 | CUM | 14101 | F10-Lift Wall-M50 | Lift Wall-M50
171 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC167 | PL1298-Building 1-F10-ZC167 | 1339932.01 | 97.891 | CUM | 13688 | F10-PT Beam-M40 | PT Beam-M40
172 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC168 | PL1298-Building 1-F10-ZC168 | 9516992.64 | 695.280 | CUM | 13688 | F10-PT Slab-M40 | PT Slab-M40
173 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC169 | PL1298-Building 1-F10-ZC169 | 300970.8 | 23.400 | CUM | 12862 | F10-RCC Beam-M30 | RCC Beam-M30
174 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC170 | PL1298-Building 1-F10-ZC170 | 320649.66 | 24.930 | CUM | 12862 | F10-RCC Slab-M30 | RCC Slab-M30
175 | F10-Rmc-Conventional | F10-W-Rmc-Con | 14805077.8 | ZC171 | PL1298-Building 1-F10-ZC171 | 105018.23 | 8.165 | CUM | 12862 | F10-Staircase-M30 | Staircase-M30
176 | F10-Reinforcement | F10-W-Reinf | 7260389.15 | ZC172 | PL1298-Building 1-F10-ZC172 | 7260389.15 | 92,772.670 | KGS | 78.26 | F10-Reinforcement Steel | Reinforcement Steel
177 | F10-PT Tendons | F10-W-Pt | 2251601.66 | ZC173 | PL1298-Building 1-F10-ZC173 | 2251601.66 | 13,629.550 | KGS | 165.2 | F10-PT Strand-Tendon | PT Strand-Tendon
178 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC174 | PL1298-Building 1-F11-ZC174 | 2057899.94 | 145.940 | CUM | 14101 | F11-Column-M50 | Column-M50
179 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC175 | PL1298-Building 1-F11-ZC175 | 1163614.52 | 82.520 | CUM | 14101 | F11-Lift Wall-M50 | Lift Wall-M50
180 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC176 | PL1298-Building 1-F11-ZC176 | 1339932.01 | 97.891 | CUM | 13688 | F11-PT Beam-M40 | PT Beam-M40
181 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC177 | PL1298-Building 1-F11-ZC177 | 9516992.64 | 695.280 | CUM | 13688 | F11-PT Slab-M40 PT Slab-M40 Page 11 | of Report By StrategicERP 17
182 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC178 | PL1298-Building 1-F11-ZC178 | 300970.8 | 23.400 | CUM | 12862 | F11-RCC Beam-M30 | RCC Beam-M30
183 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC179 | PL1298-Building 1-F11-ZC179 | 320649.66 | 24.930 | CUM | 12862 | F11-RCC Slab-M30 | RCC Slab-M30
184 | F11-Rmc-Conventional | F11-W-Rmc-Con | 14805077.8 | ZC180 | PL1298-Building 1-F11-ZC180 | 105018.23 | 8.165 | CUM | 12862 | F11-Staircase-M30 | Staircase-M30
185 | F11-Reinforcement | F11-W-Reinf | 7446512.56 | ZC181 | PL1298-Building 1-F11-ZC181 | 7446512.56 | 95,150.940 | KGS | 78.26 | F11-Reinforcement Steel | Reinforcement Steel
186 | F11-PT Tendons | F11-W-Pt | 2251601.66 | ZC182 | PL1298-Building 1-F11-ZC182 | 2251601.66 | 13,629.550 | KGS | 165.2 | F11-PT Strand-Tendon | PT Strand-Tendon
187 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC183 | PL1298-Building 1-TF-ZC183 | 1228761.14 | 87.140 | CUM | 14101 | TT-Column-M50 | Column-M50
188 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC184 | PL1298-Building 1-TF-ZC184 | 1028526.94 | 72.940 | CUM | 14101 | TT-Lift Wall-M50 | Lift Wall-M50
189 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC185 | PL1298-Building 1-TF-ZC185 | 889172.48 | 64.960 | CUM | 13688 | TT-PT Beam-M40 | PT Beam-M40
190 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC186 | PL1298-Building 1-TF-ZC186 | 7745354.8 | 565.850 | CUM | 13688 | TT-PT Slab-M40 | PT Slab-M40
191 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC187 | PL1298-Building 1-TF-ZC187 | 390876.18 | 30.390 | CUM | 12862 | TT-RCC Beam-M30 | RCC Beam-M30
192 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC188 | PL1298-Building 1-TF-ZC188 | 554480.82 | 43.110 | CUM | 12862 | TT-RCC Slab-M30 | RCC Slab-M30
193 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC189 | PL1298-Building 1-TF-ZC189 | 170164.26 | 13.230 | CUM | 12862 | TT-Staircase-M30 | Staircase-M30
194 | TF-Rmc-Conventional | TF-W-Rmc-Con | 12373646.38 | ZC189A | PL1298-Building 1-TF-ZC189A | 366309.76 | 28.480 | CUM | 12862 | TT-Parapet-M35 | Parapet-M35
195 | TF-Reinforcement | TF-W-Reinf | 7446512.56 | ZC190 | PL1298-Building 1-TF-ZC190 | 7446512.56 | 95,150.940 | KGS | 78.26 | TT-Reinforcement Steel | Reinforcement Steel
196 | TF-PT Tendons | TF-W-Pt | 2251601.66 | ZC191 | PL1298-Building 1-TF-ZC191 | 2251601.66 | 13,629.550 | KGS | 165.2 | TT-PT Strand-Tendon | PT Strand-Tendon
197 | AT-Rmc-Conventional | AT-W-Rmc-Con | 2257288.08 | ZC192 | PL1298-Building 1-AT-ZC192 | 1228761.14 | 87.140 | CUM | 14101 | AT-Column-M50 | Column-M50
198 | AT-Rmc-Conventional | AT-W-Rmc-Con | 2257288.08 | ZC193 | PL1298-Building 1-AT-ZC193 | 1028526.94 | 72.940 | CUM | 14101 | AT-Lift Wall-M50 | Lift Wall-M50
199 | AT-Reinforcement | AT-W-Reinf | 807585.29 | ZC194 | PL1298-Building 1-AT-ZC194 | 807585.29 | 10,319.260 | KGS | 78.26 | AT-Reinforcement Steel | Reinforcement Steel
200 | ALL-Blockwork | ALL-W-Blockwork 1 Page 12 of Report By StrategicERP | 15936103.97 | ZC195 | PL1298-Building 1-ALL-ZC195 | 15936103.97 | 11,730.230 | SQM | 1358.55 | ALL-Block work | Block work
201 | ALL-Internal Plaster | ALL-W-Internal Plaster | 4948683.41 | ZC196 | PL1298-Building 1-ALL-ZC196 | 827237.7 | 1,361.260 | SQM | 607.7 | ALL-Ceiling Plaster | Ceiling Plaster
202 | ALL-Internal Plaster | ALL-W-Internal Plaster | 4948683.41 | ZC197 | PL1298-Building 1-ALL-ZC197 | 4121445.71 | 6,782.040 | SQM | 607.7 | ALL-Internal Wall Plaster | Internal Wall Plaster
203 | ALL-External Plaster | ALL-W-External Plaster | 6443804.92 | ZC198 | PL1298-Building 1-ALL-ZC198 | 6443804.92 | 7,974.710 | SQM | 808.03 | ALL-External Plaster | External Plaster
204 | ALL-Gypsum Plaster | ALL-W-Gypsum Plaster | 16352506.08 | ZC199 | PL1298-Building 1-ALL-ZC199 | 16352506.08 | 38,494.600 | SQM | 424.8 | ALL-Gypsum Plaster | Gypsum Plaster
205 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC200 | PL1298-Building 1-ALL-ZC200 | 3279569.28 | 2,895.100 | SQM | 1132.8 | ALL-Box Type Waterproofing - Basement Raft, Stitch Raft | Box Type Waterproofing - Basement Raft, Stitch Raft
206 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC201 | PL1298-Building 1-ALL-ZC201 | 264426.2 | 224.090 | SQM | 1180 | ALL-Box TypeWaterproofing - Lift Pit,R.W.Paradi | Box TypeWaterproofing - Lift Pit,R.W.Paradi
207 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC202 | PL1298-Building 1-ALL-ZC202 | 952062.08 | 478.010 | SQM | 1991.72 | ALL-Brick Bat waterproofing+Chemical- Toilet-200MM Sunk | Brick Bat waterproofing+Chemical-Toilet-200MM Sunk
208 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC203 | PL1298-Building 1-ALL-ZC203 | 1086956.64 | 601.010 | SQM | 1808.55 | ALL-Brick Bat waterproofing+Chemical - Attached Terrace-150MM Sunk | Brick Bat waterproofing+Chemical -Attached Terrace- 150MM Sunk
209 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC204 | PL1298-Building 1-ALL-ZC204 | 469762.27 | 326.140 | SQM | 1440.37 | ALL-Base Coat/Chemical Coat -Refuge Area-100MM Sunk | Base Coat/Chemical Coat -Refuge Area-100MM Sunk
210 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC205 | PL1298-Building 1-ALL-ZC205 | 2954809.68 | 2,086.730 | SQM | 1416 | ALL-Brick Bat Waterproofing+Chemical - Top terrace-250MM Sunk | Brick Bat Waterproofing+Chemical -Top terrace-250MM Sunk
211 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC206 | PL1298-Building 1-ALL-ZC206 | 176716.8 | 124.800 | SQM | 1416 | ALL-Brick Bat Waterproofing-OHWT (Bottom) | Brick Bat Waterproofing-OHWT (Bottom)
212 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC207 | PL1298-Building 1-ALL-ZC207 | 176716.8 | 124.800 | SQM | 1416 | ALL-Brick Bat Waterproofing with IPS Finish-LMR & OHWT (Top) | Brick Bat Waterproofing with IPS Finish-LMR & OHWT (Top)
213 | ALL-Waterp | ALL-W-Waterp | 9579864.67 | ZC208 | PL1298-Building 1-ALL-ZC208 | 218844.92 | 360.120 | SQM | 607.7 | ALL-Inside Waterproof plaster-OHWT Wall/Paradi (IPS Finish) | Inside Waterproof plaster-OHWT Wall/Paradi (IPS Finish)
214 | ALL-Doors | ALL-W-Doors | 8657945.95 | ZC209 | PL1298-Building 1-ALL-ZC209 | 8657945.95 | 1.000 | NOS | 8657945.95 | ALL-Doors & Wooden Works | Doors & Wooden Works
215 | ALL-Sliding Windows | ALL-W-Sliding Windows | 8148655.01 | ZC210 | PL1298-Building 1-ALL-ZC210 | 8148655.01 | 1.000 | NOS | 8148655.01 | ALL-Windows & Sliding Doors | Windows & Sliding Doors
216 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC211 | PL1298-Building 1-ALL-ZC211 | 7703642.79 | 6,414.090 | SQM | 1201.05 | ALL-Trimix- Ramp Area/Driveways | Trimix- Ramp Area/Driveways
217 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC212 | PL1298-Building 1-ALL-ZC212 | 3546432.43 | 4,337.560 | SQM | 817.61 | ALL-PU Coating Paint - Basement- 1Parking& Podium-1,2&3 Parking PU Coating Paint | - Basement-1Parking& Podium-1,2&3 Parking Page 13 of Report By StrategicERP 17
218 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC213 | PL1298-Building 1-ALL-ZC213 | 337522.29 | 326.140 | SQM | 1034.9 | ALL-600 x 600 mm Vitrified Tile (Double Charge) -Refuge Area | 600 x 600 mm Vitrified Tile (Double Charge) -Refuge Area
219 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC214 | PL1298-Building 1-ALL-ZC214 | 75920.26 | 73.360 | SQM | 1034.9 | ALL-Other room-/Driver room/Cafeteria- Vitrified 600x600 | Other room-/Driver room/Cafeteria-Vitrified 600x600
220 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC215 | PL1298-Building 1-ALL-ZC215 | 449069.97 | 482.430 | SQM | 930.85 | ALL-300 x 300 mm Antiskid Tiles - All Toilets | 300 x 300 mm Antiskid Tiles - All Toilets
221 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC216 | PL1298-Building 1-ALL-ZC216 | 3552560.88 | 2,687.730 | SQM | 1321.77 | ALL-600 X 600 mm Rustic Finish- common terrace & office terrace | 600 X 600 mm Rustic Finish- common terrace & office terrace
222 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC217 | PL1298-Building 1-ALL-ZC217 | 9658789.68 | 2,171.100 | SQM | 4448.8 | ALL-Premium Granite & Tile Combination - Floor Comman Lobby,Wide Passage etc | Premium Granite & Tile Combination - Floor Comman Lobby,Wide Passage etc
223 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC218 | PL1298-Building 1-ALL-ZC218 | 1604279.66 | 196.240 | SQM | 8175.09 | ALL-Designer Italian Marble - Main Entrance Lobby (East & West Side) (Granite + Tile Combination as per Interior) | Designer Italian Marble - Main Entrance Lobby (East & West Side) (Granite + Tile Combination as per Interior)
224 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC219 | PL1298-Building 1-ALL-ZC219 | 821417.65 | 458.020 | SQM | 1793.41 | ALL-150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing | 150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing
225 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC220 | PL1298-Building 1-ALL-ZC220 | 898091.4 | 423.650 | SQM | 2119.89 | ALL-Steel Grey Granite-Tread-300 mm wide | Steel Grey Granite-Tread-300 mm wide
226 | ALL-Flooring | ALL-W-Flooring | 29197562.88 | ZC221 | PL1298-Building 1-ALL-ZC221 | 549835.87 | 259.370 | SQM | 2119.89 | ALL-Steel Grey Granite-Riser-150 mm height | Steel Grey Granite-Riser-150 mm height
227 | ALL-Skirting | ALL-W-Skirting | 1297931.43 | ZC222 | PL1298-Building 1-ALL-ZC222 | 456009.94 | 3,206.370 | RMT | 142.22 | ALL-Common lobby/Refuge Area/Driver room/Cafeteri-Vitrified 600x600 | Common lobby/Refuge Area/Driver room/Cafeteri-Vitrified 600x600
228 | ALL-Skirting | ALL-W-Skirting | 1297931.43 | ZC223 | PL1298-Building 1-ALL-ZC223 | 589405.8 | 575.350 | RMT | 1024.43 | ALL-150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing | 150 X 600 mm Rustic FinishTile with Gray granite edging - Floor landing & Mid landing
229 | ALL-Skirting | ALL-W-Skirting | 1297931.43 | ZC224 | PL1298-Building 1-ALL-ZC224 | 252515.69 | 772.550 | RMT | 326.86 | ALL-Steel Grey Granite -Staircase- Tread Riser | Steel Grey Granite -Staircase- Tread Riser
230 | ALL-Dado | ALL-W-Dado | 3814499.99 | ZC225 | PL1298-Building 1-ALL-ZC225 | 3754216.94 | 2,421.310 | SQM | 1550.49 | ALL-300 X 600 mm Digital Ceramic Tile- Dado-Toilets-upto Lintel Ht. | 300 X 600 mm Digital Ceramic Tile-Dado-Toilets-upto Lintel Ht.
231 | ALL-Dado | ALL-W-Dado | 3814499.99 | ZC226 | PL1298-Building 1-ALL-ZC226 | 60283.05 | 38.880 | SQM | 1550.49 | ALL-300 X 600 mm Digital Ceramic Tile- Kitchen/Pantry-Dado-(2Ft aboveKitchen Otta) | 300 X 600 mm Digital Ceramic Tile-Kitchen/Pantry-Dado- (2Ft aboveKitchen Otta)
232 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC227 | PL1298-Building 1-ALL-ZC227 | 1577549.72 | 344.250 | SQM | 4582.57 | ALL- Granite+Tile Combination as per interior design - Lift Cladding & | Jams-Full Ht. Wall Cladding Cladding & Jams-Full Ht. Wall Cladding
233 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC228 | PL1298-Building 1-ALL-ZC228 | 2493836.02 | 264.730 | SQM | 9420.3 | ALL-Italian Marble/Black Granite/Wall Paper -West & East Side Entrance Lobby -Full Ht. Wall Cladding | Italian Marble/Black Granite/Wall Paper -West & East Side Entrance Lobby -Full Ht. Wall Cladding
234 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC229 | PL1298-Building 1-ALL-ZC229 | 147147.78 | 29.160 | RMT | 5046.22 | ALL-Granite with Black kadappa Matt Finish-Kitchen/Pantry Otta | Granite with Black kadappa Matt Finish-Kitchen/Pantry Otta
235 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC230 | PL1298-Building 1-ALL-ZC230 | 304326.06 | 43.490 | SQM | 6997.61 | ALL-Black Granite-Washbasin Counter | Black Granite-Washbasin Counter
236 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC231 | PL1298-Building 1-ALL-ZC231 | 71156.67 | 151.950 | RMT | 468.29 | ALL-Granite & Ply Combination with laminate - Toilet Door Frame Granite & Ply Combination | with laminate - Toilet Door Frame Page 14 of Report By StrategicERP 17
237 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC232 | PL1298-Building 1-ALL-ZC232 | 1762775.12 | 1,361.700 | RMT | 1294.54 | ALL-Black Granite Patti -@ Bund Wall- Below Glazing | Black Granite Patti -@ Bund Wall-Below Glazing
238 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC233 | PL1298-Building 1-ALL-ZC233 | 38195.46 | 63.550 | RMT | 601.03 | ALL-Black Granite Patti -@Office Attached Terrace - Door Frame | Black Granite Patti -@Office Attached Terrace - Door Frame
239 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC234 | PL1298-Building 1-ALL-ZC234 | 209750.94 | 466.020 | RMT | 450.09 | ALL-Steel Grey Granite - Ventilator Frame | Steel Grey Granite - Ventilator Frame
240 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC235 | PL1298-Building 1-ALL-ZC235 | 265021.99 | 588.820 | RMT | 450.09 | ALL-Steel Grey Granite - Window Bottom Patti | Steel Grey Granite - Window Bottom Patti
241 | ALL-Granite & Stone Work | ALL-W-Granite & Stone Work | 7326797.11 | ZC236 | PL1298-Building 1-ALL-ZC236 | 457037.35 | 353.050 | RMT | 1294.54 | ALL-Black Granite Patti -@Toilet Ledge Wall Patti | Black Granite Patti -@Toilet Ledge Wall Patti
242 | ALL-Fabrication Work | ALL-W-Fabrication Work | 4583618.44 | ZC237 | PL1298-Building 1-ALL-ZC237 | 4583618.44 | 1.000 | NOS | 4583618.44 | ALL-MS & SS Works- Grills & Railings | MS & SS Works- Grills & Railings
243 | ALL-Painting Work | ALL-W-Paint | 10185818.76 | ZC238 | PL1298-Building 1-ALL-ZC238 | 10185818.76 | 1.000 | NOS | 10185818.76 | ALL-Painting & Polishing Works | Painting & Polishing Works
244 | ALL-Internal Plumbing | ALL-W-Plumb | 5655000 | ZC239 | PL1298-Building 1-ALL-ZC239 | 5655000 | 1.000 | NOS | 5655000 | ALL-Plumbing work-3BHK | Plumbing work-3BHK
245 | ALL-Internal Electrical | ALL-W-Elect | 5843360 | ZC240 | PL1298-Building 1-ALL-ZC240 | 5843360 | 1.000 | NOS | 5843360 | ALL-Electrical work-3BHK | Electrical work-3BHK
246 | ALL-Glazing & Facade Work | ALL-W-Glazing & Facade Work | 108733615.31 | ZC241 | PL1298-Building 1-ALL-ZC241 | 108733615.31 | 1.000 | NOS | 108733615.31 | ALL-Elevation, Glazing, Facade Work | Elevation, Glazing, Facade Work
247 | ALL-Lift Work | ALL-W-Lift Work | 128578700 | ZC242 | PL1298-Building 1-ALL-ZC242 | 125103600 | 6.000 | NOS | 20850600 | ALL-Lift 1-2.5X1.90 | Lift 1-2.7X2.65
248 | ALL-Lift Work | ALL-W-Lift Work | 128578700 | ZC243 | PL1298-Building 1-ALL-ZC243 | 3475100 | 1.000 | NOS | 3475100 | ALL-Lift 2-1.90X1.90 | Lift 2-2.4X3.0
249 | ALL-Building Firefighting | ALL-W-Bldg Ff | 30557456.29 | ZC244 | PL1298-Building 1-ALL-ZC244 | 30557456.29 | 1.000 | NOS | 30557456.29 | ALL-Buildings Fire Fighting Work | Buildings Fire Fighting Work
250 | ALL-Building Amenities | ALL-W-Amenities | 31321392.7 | ZC245 | PL1298-Building 1-ALL-ZC245 | 31321392.7 | 1.000 | NOS | 31321392.7 | ALL-Bldg Amenities | Bldg Amenities
251 | ALL-Miscellaneous Work | ALL-W-Misc Work | 5092909.38 | ZC246 | PL1298-Building 1-ALL-ZC246 | 5092909.38 | 1.000 | NOS | 5092909.38 | ALL-Misc, Dep. Labour, Cleaning | Misc, Dep. Labour, Cleaning
252 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.1 | PL1298-Building 1-F12-ZC182.1 | 1800697.7 | 127.700 | CUM | 14101 | F11-Column-M50 Column-M50 Page 15 of | Report By StrategicERP 17
253 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.2 | PL1298-Building 1-F12-ZC182.2 | 1018233.21 | 72.210 | CUM | 14101 | F11-Lift Wall-M50 | Lift Wall-M50
254 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.3 | PL1298-Building 1-F12-ZC182.3 | 1339918.32 | 97.890 | CUM | 13688 | F11-PT Beam-M40 | PT Beam-M40
255 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.4 | PL1298-Building 1-F12-ZC182.4 | 9448552.64 | 690.280 | CUM | 13688 | F11-PT Slab-M40 | PT Slab-M40
256 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.5 | PL1298-Building 1-F12-ZC182.5 | 300970.8 | 23.400 | CUM | 12862 | F11-RCC Beam-M30 | RCC Beam-M30
257 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.6 | PL1298-Building 1-F12-ZC182.6 | 320649.66 | 24.930 | CUM | 12862 | F11-RCC Slab-M30 | RCC Slab-M30
258 | F12-Rmc-Conventional | F12-W-Rmc-Con | 14346581.01 | ZC182.7 | PL1298-Building 1-F12-ZC182.7 | 117558.68 | 9.140 | CUM | 12862 | F11-Staircase-M30 | Staircase-M30
259 | F12-Reinforcement | F12-W-Reinf | 7688899.44 | ZC182.8 | PL1298-Building 1-F12-ZC182.8 | 7688899.44 | 98,248.140 | KGS | 78.26 | F11-Reinforcement Steel | Reinforcement Steel
260 | F12-PT Tendons | F12-W-Pt | 2251601.66 | ZC182.9 | PL1298-Building 1-F12-ZC182.9 | 2251601.66 | 13,629.550 | KGS | 165.2 | F11-PT Strand-Tendon | PT Strand-Tendon
261 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.1 | PL1298-Building 1-F13-ZC183.1 | 1800697.7 | 127.700 | CUM | 14101 | F11-Column-M50 | Column-M50
262 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.2 | PL1298-Building 1-F13-ZC183.2 | 1018233.21 | 72.210 | CUM | 14101 | F11-Lift Wall-M50 | Lift Wall-M50
263 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.3 | PL1298-Building 1-F13-ZC183.3 | 1339918.32 | 97.890 | CUM | 13688 | F11-PT Beam-M40 | PT Beam-M40
264 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.4 | PL1298-Building 1-F13-ZC183.4 | 9448552.64 | 690.280 | CUM | 13688 | F11-PT Slab-M40 | PT Slab-M40
265 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.5 | PL1298-Building 1-F13-ZC183.5 | 300970.8 | 23.400 | CUM | 12862 | F11-RCC Beam-M30 | RCC Beam-M30
266 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.6 | PL1298-Building 1-F13-ZC183.6 | 320649.66 | 24.930 | CUM | 12862 | F11-RCC Slab-M30 | RCC Slab-M30
267 | F13-Rmc-Conventional | F13-W-Rmc-Con | 14346581.01 | ZC183.7 | PL1298-Building 1-F13-ZC183.7 | 117558.68 | 9.140 | CUM | 12862 | F11-Staircase-M30 | Staircase-M30
268 | F13-Reinforcement | F13-W-Reinf | 7688899.44 | ZC183.8 | PL1298-Building 1-F13-ZC183.8 | 7688899.44 | 98,248.140 | KGS | 78.26 | F11-Reinforcement Steel | Reinforcement Steel
269 | F13-PT Tendons | F13-W-Pt | 2251601.66 | ZC183.9 | PL1298-Building 1-F13-ZC183.9 | 2251601.66 | 13,629.550 | KGS | 165.2 | F11-PT Strand-Tendon | PT Strand-Tendon
270 | OHWT-Rmc-Conventional | OHWT-W-Rmc-Con | 4446191.03 | ZC252 | PL1298-Building 1--ZC252 | 544862.64 | 38.640 | CUM | 14101 | OHWT-Column-M40 | Column-M40
271 | OHWT-Rmc-Conventional | OHWT-W-Rmc-Con | 4446191.03 | ZC253 | PL1298-Building 1--ZC253 | 1272051.21 | 90.210 | CUM | 14101 | OHWT-Lift Wall-M40 | Lift Wall-M40
272 | OHWT-Rmc-Conventional | OHWT-W-Rmc-Con | 4446191.03 | ZC254 | PL1298-Building 1--ZC254 | 1349636.8 | 98.600 | CUM | 13688 | OHWT-PT Slab-M35 PT Slab-M35 Page 16 | of Report By StrategicERP 17
273 | OHWT-Rmc-Conventional | OHWT-W-Rmc-Con | 4446191.03 | ZC255 | PL1298-Building 1--ZC255 | 86689.88 | 6.740 | CUM | 12862 | OHWT-RCC Beam-M35 | RCC Beam-M35
274 | OHWT-Rmc-Conventional | OHWT-W-Rmc-Con | 4446191.03 | ZC256 | PL1298-Building 1-AT-ZC256 | 1192950.5 | 92.750 | CUM | 12862 | RCC-OHWT Pardi-OHWT bottom slab to OHWT top slab-M-40 RCC-OHWT | Pardi-OHWT bottom slab to OHWT top slab-M- 40
275 | OHWT-Reinforcement | OHWT-W-Reinf | 1994647.84 | ZC256 | PL1298-Building 1--ZC256 | 1994647.84 | 25,487.450 | KGS | 78.26 | OHWT-Reinforcement Steel Reinforcement Steel Page 17 | of Report By StrategicERP 17